## Prototype Tracker
PRESALES | [84 empty] | CONSTRUCTION
Source | Status | CRM | CRM | CRM | CRM | CRM | CRM | CRM | Email | Ricardy | Ricardy |  |  | Ricardy |  |  | Ricardy |  |  | Ricardy |  |  | Ricardy |  |  | Ricardy |  |  | Ricardy |  |  | Ricardy |  |  | Ricardy |  | Ricardy |  | BD | [30 empty] | BD
Column1 | Design Stage | Opp Name | Opp ID | Deal Type | Property Type | Deal Stage | BD Name | #Units | Receive date | Kickoff date | ROM Request | ROM Request Forecast | Days Passed Since ROM Request | ROM Receive | ROM Receive Forecast | Days Passed Since ROM Received | Backhaul Cost Request | Backhaul Cost Request Forecast | Days Since BC Request | Backhaul Cost Receive | Backhaul Cost Receive Forecast | Days Since BC Received | OSP Request | OSP Request Forecast | Days Since OSP Request | OSP Receive | OSP Receive Forecast | Days Since OSP Received | FM Request | FM Request Forecast | Days Since FM Request | FM receive | FM Receive Forecast | Days Since FM Received | FM review | FM Review Forecast | FM Approval meeting | 1-pager Submission to BD | Proposal Accepted | Proposal Acceptance Forecast | Days Since Proposal Accepted | Firm Pricing request | Firm Pricing Request Forecast | Days Since Firm Pricing Request | Site Walk | Site Walk Forecast | Days Since Site Walk | Firm Quote Receival | Firm Quote Receival Forecast | Days Since Firm Quote Receival | Final Design & BOM(20 calendar days from site walk) | Final Design & BOM Forecast | Days Since Final Design & BOM | FM Request 2 | FM Request 2 Forecast | Days Since FM Request 2 | FM Review 2 | FM Review 2 Forecast | Days Since FM Review 2 | Tax Review | Tax Review Forecast | Days Since Tax Review | Tax Approval | Tax Approval Forecast | Days Since Tax Approval | Final proposal submission | Final Proposal Submission Forecast | Days Since Final Proposal Submission | CAC Presentation (If applicable) | BD submits proposal | BD Submits Proposal Forecast | Days Since BD Submitted Proposal | Final Proposal Accepted | Final Proposal Acceptance Forecast | Days Since Final Proposal Accepted | Legal Agreement | Legal Agreement Forecast | Days Since Legal Agreement | Executed Agreement | Executed Agreement Forecast | Days Since Executed Agreement | Construction Stage | Site Name | Site ID | A&E Request | A&E Request Forecast | Days Since A&E Request | A&E receive | A&E Receive Forecast | Days Since A&E Receive | Budget Request | Budget Request Forecast | Days Since Budget Request | Budget Approval | Budget Approval Forecast | Days Since Budget Approval | Quotes from OEM | PO Request for OEM | PO Request for OEM Forecast | Days Since PO Request for OEM | PO Approval | PO Approval Forecast | Days Since PO Approval | backhaul ordered | Backhaul Order Forecast | Days Since Backhaul Order | RTP Request | RTP Request Forecast | Days Since RTP Request | RTP Approved | RTP Approval Forecast | Days Since RTP Approval | RFP Request | RFP Request Forecast | Days Since RFP Request | RFP Received | RFP Received Forecast | Days Since RFP Received | PO for GC Request | PO for GC Request Forecast | Days Since PO for GC Request | PO for GC Approved | PO for GC Approval Forecast | Days Since PO for GC Approval | Construction Start | Construction Start Forecast | Days Since Construction Start | Construction Complete | Construction Complete Forecast | Days Since Construction Complete | Build (6 months) | Integration Start | Integration Start Forecast | Days Since Integration Start | Integration Complete | Integration Complete Forecast | Days Since Integration Complete | Close Out Package(2weeks from integration complete | Close Out Package Forecast | Days Since Close Out Package | Acceptance testing 2 weeks from close out package) | Acceptance Testing Forecast | Days Since Acceptance Testing | Customer acceptance(1 month after acceptance testing) | Customer Acceptance Forecast | Days Since Customer Acceptance | Operations handoff(1 week after customer acceptance) | Operations Handoff Forecast | Days Since Operations Handoff | FNE Date | FNE Date Forecast | Days Since FNE Date | FNE Notice | FNE Notice Forecast | Days Since FNE Notice | PMDB Update | Revenue Billing(PMDB)
| Completed | Carson Estates |  | Connected Venues |  |  | Christina | 262 | 2025-01-01 | 2025-02-01 | 2025-06-12 | 2025-02-11 | 23 | 2025-06-09 | 2025-06-26 | 26 | 2025-05-13 | 2025-07-17 | 45 | 2025-05-30 | 2025-08-07 | 32 | 2025-02-01 | 2025-07-28 | 116 | 2025-06-10 | 2025-08-11 | 25 | 2025-02-01 | 2025-02-11 | 116 | 2025-05-16 | 2025-02-13 | 42 |  | 2025-02-17 |  | 2025-02-24 | 2025-06-01 | 2025-03-05 |  | 2025-06-16 | 2025-03-14 | 21 |  | 2025-03-25 | 32751 |  | 2025-04-03 | 32751 |  | 2025-04-14 | 32751 |  | 2025-04-23 | 32751 |  | 2025-05-02 |  |  | 2025-05-13 | 32751 | 2025-01-01 | 1900-01-09 | 139 | 2025-01-05 | 1900-01-18 | 136 | 2025-01-06 |  | 1900-01-29 | 32751 | 2025-03-01 | 1900-02-07 | 96 |  | 2025-07-04 | 32751 |  | 2025-07-18 | 32751 | C. Design | Chacra Canyon |  | 2020-01-01 | 1900-01-09 | 1444 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Site Mod - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
| Completed | UT_Valley of Wildflower (Lennar development) |  | Connected Communities |  |  | Ramith | 1 | 2025-04-26 | 2025-05-06 | 2025-05-13 | 2025-05-15 | 45 | 2025-06-15 | 2025-05-27 | 21 | 2025-06-13 | 1900-01-04 | 22 | 2025-06-30 | 1900-01-25 | 11 | 2025-05-06 | 1900-01-15 | 50 | 2025-01-04 | 1900-01-29 | 136 | 2025-05-06 | 2025-05-15 | 50 |  | 2025-05-19 | 32751 |  | 2025-05-21 |  | 2025-05-27 | 2025-06-15 | 2025-06-05 | 21 |  | 2025-06-16 | 32751 |  | 2025-06-25 | 32751 |  | 2025-07-04 | 32751 |  | 2025-07-15 | 32751 |  | 2025-07-24 | 32751 |  | 2025-08-04 |  |  | 2025-08-13 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Musculoskeletal Institute (EP MSK) |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 | 2025-05-30 | 1900-05-11 | 32 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
| Completed | AL_The Hub at Grants Hill |  | Connected Venues |  |  | Steven | 350 | 2025-04-30 | 2025-05-07 | 2025-05-19 | 2025-05-16 | 41 | 2025-06-03 | 2025-06-02 | 30 | 2025-04-10 | 2025-06-23 | 68 | 2025-04-29 | 1899-12-31 | 55 | 2025-05-07 | 2025-07-02 | 49 | 2025-03-01 | 2025-07-16 | 96 | 2025-05-07 | 2025-05-16 | 49 |  | 2025-05-20 | 32751 |  | 2025-05-22 |  | 2025-05-24 |  | 2025-06-03 | 32751 |  | 2025-06-12 | 32751 |  | 2025-06-23 | 32751 |  | 2025-07-02 | 32751 |  | 2025-07-11 | 32751 |  | 2025-07-22 | 32751 |  | 2025-07-31 |  |  | 2025-08-11 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory University Hospital Midtown |  | 2025-02-18 | 1900-01-09 | 105 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45736 | 1900-03-15 | 83 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 | 2025-03-28 | 1900-04-23 | 77 |  | 1900-05-02 | 32751 | 2025-05-30 | 1900-05-11 | 32 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Done | Completed | FL_Green District |  | Connected Venues/Wifi |  |  | Ramith | 6955 | 2025-05-03 | 2025-05-13 | 2025-03-18 | 2025-05-22 | 85 | 2025-04-02 | 2025-04-01 | 74 | 2025-05-15 | 2025-04-22 | 43 | 2025-04-24 | 2025-05-13 | 58 | 2025-05-13 | 2025-05-01 | 45 | 2025-04-24 | 2025-05-15 | 58 | 2025-05-13 | 2025-05-22 | 45 |  | 2025-05-26 | 32751 |  | 2025-05-28 |  | 2025-06-01 |  | 2025-06-10 | 32751 |  | 2025-06-19 | 32751 |  | 2025-06-30 | 32751 |  | 2025-07-09 | 32751 |  | 2025-07-18 | 32751 |  | 2025-07-29 | 32751 |  | 2025-08-07 |  |  | 2025-08-18 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Glenwood Canyon ATT Additional Node |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | No FNE since this is just a Site Mod. | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Hold | On Hold | Canvas at Wildwood |  | Connected Communities |  |  | Tyrone | 264 | 2025-05-04 | 2025-05-19 | 2025-03-18 | 2025-05-28 | 85 | 2025-04-21 | 2025-04-01 | 61 | 2025-05-30 | 2025-04-22 | 32 | 2025-06-21 | 2025-05-13 | 16 | 2025-05-19 | 2025-05-01 | 41 | 2025-05-02 | 2025-05-15 | 52 | 2025-05-19 | 2025-05-28 | 41 |  | 2025-05-30 | 32751 |  | 2025-06-03 |  | 2025-05-30 |  | 2025-06-10 | 32751 |  | 2025-06-19 | 32751 |  | 2025-06-30 | 32751 |  | 2025-07-09 | 32751 |  | 2025-07-18 | 32751 |  | 2025-07-29 | 32751 |  | 2025-08-07 |  |  | 2025-08-18 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Glenwood Canyon Backup Power |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 | 2020-01-01 | 1900-01-12 | 1444 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | No FNE since this is just a Site Mod. | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Lost | Completed | The Estates at Hurstmont |  | Connected Venues |  |  | Tyrone | 210 | 2025-05-08 | 2025-05-20 | 2025-04-14 | 2025-05-29 | 66 | 2025-05-02 | 2025-04-28 | 52 | 2025-04-14 | 2025-05-19 | 66 | 2025-05-13 | 2025-06-09 | 45 | 2025-05-20 | 2025-05-28 | 40 | 2025-05-16 | 2025-06-11 | 42 | 2025-05-20 | 2025-05-29 | 40 | 2025-05-15 | 2025-06-02 | 43 |  | 2025-06-04 |  | 2025-05-28 |  | 2025-06-06 | 32751 |  | 2025-06-17 | 32751 |  | 2025-06-26 | 32751 |  | 2025-07-07 | 32751 |  | 2025-07-16 | 32751 |  | 2025-07-25 | 32751 |  | 2025-08-05 |  |  | 2025-08-14 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Laurens MRI |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Site Mod - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
FM | Completed | Alyster |  | Connected Communities |  |  | Christina | 102 | 2025-05-09 | 2025-05-24 | 2025-05-06 | 2025-06-03 | 50 | 2025-05-21 | 2025-05-20 | 39 | 2025-05-06 | 2025-06-10 | 50 | 2025-05-19 | 2025-07-01 | 41 | 2025-05-24 | 2025-06-19 | 36 | 2025-05-21 | 2025-07-03 | 39 | 2025-05-24 | 2025-06-03 | 36 | 2025-05-22 | 2025-06-05 | 38 |  | 2025-06-09 |  | 2025-06-02 |  | 2025-06-11 | 32751 |  | 2025-06-20 | 32751 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 | 32751 |  | 2025-08-08 |  |  | 2025-08-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Minnesota State Fairgrounds |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 | 2023-09-25 | 1900-05-25 | 471 | 2024-03-13 | 1900-06-22 | 349 |  | 2024-03-13 | 1900-07-06 | 349 | 2024-03-13 | 1900-07-20 | 349 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Radio Swap - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Hold | On Hold | eleva |  | Connected Communities |  |  | Christina | 151 | 2025-05-10 | 2025-05-22 | 2025-01-22 | 2025-06-02 | 124 | 2025-05-21 | 2025-02-05 | 39 | 2025-05-30 | 2025-02-26 | 32 | 2025-06-19 | 2025-03-19 | 18 | 2025-05-22 | 2025-03-07 | 38 |  | 2025-03-21 | 32751 | 2025-05-22 | 2025-06-02 | 38 |  | 2025-06-04 | 32751 |  | 2025-06-06 |  | 2025-05-24 |  | 2025-06-03 | 32751 |  | 2025-06-12 | 32751 |  | 2025-06-23 | 32751 |  | 2025-07-02 | 32751 |  | 2025-07-11 | 32751 |  | 2025-07-22 | 32751 |  | 2025-07-31 |  |  | 2025-08-11 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Mt. Sinai |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45804 | 1900-03-15 | 35 |  | 1900-03-29 | 32751 | 45804 | 1900-04-09 | 35 | 2025-06-11 | 1900-04-23 | 24 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | Need to Forecast Once GC is Awarded | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Hold | On Hold | Mondu |  | DAS |  |  | Ramith | 1 | 2025-05-12 | 2025-06-01 | 2025-04-11 | 2025-06-10 | 67 | 2025-04-28 | 2025-04-25 | 56 | 2025-04-11 | 2025-05-16 | 67 | 2025-05-02 | 2025-06-06 | 52 | 2025-06-01 | 2025-05-27 | 31 |  | 2025-06-10 | 32751 | 2025-06-01 | 2025-06-10 | 31 |  | 2025-06-12 | 32751 |  | 2025-06-16 |  | 2025-06-05 |  | 2025-06-16 | 32751 |  | 2025-06-25 | 32751 |  | 2025-07-04 | 32751 |  | 2025-07-15 | 32751 |  | 2025-07-24 | 32751 |  | 2025-08-04 | 32751 |  | 2025-08-13 |  |  | 2025-08-22 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Omni Hilton Head |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | No FNE since this is in the Sales/Business Development Phase. | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Network Takeover | In Design | Omni Nashville |  | DAS |  |  | Adam | N/A | 2025-05-14 | 2025-05-24 | 2025-04-24 | 2025-06-03 | 58 | 2025-05-10 | 2025-05-08 | 46 | 2025-05-12 | 2025-05-29 | 46 | 2025-06-01 | 2025-06-19 | 31 | 2025-05-24 | 2025-06-09 | 36 |  | 2025-06-23 | 32751 | 2025-05-24 | 2025-06-03 | 36 |  | 2025-06-05 | 32751 |  | 2025-06-09 |  | 2025-06-04 |  | 2025-06-13 | 32751 |  | 2025-06-24 | 32751 |  | 2025-07-03 | 32751 |  | 2025-07-14 | 32751 |  | 2025-07-23 | 32751 |  | 2025-08-01 | 32751 |  | 2025-08-12 |  |  | 2025-08-21 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Packing District: High Point Climbing |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | No FNE since this is just additional customer/client adds | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Hold | FM Request | Northern Nevada Sierra |  | DAS |  |  | Adam | N/A - 1 Bulding | 2025-05-16 | 2025-05-26 | 2025-04-29 | 2025-06-04 | 55 | 2025-05-19 | 2025-05-13 | 41 | 2025-05-23 | 2025-06-03 | 37 | 2025-06-15 | 2025-06-24 | 21 | 2025-05-26 | 2025-06-12 | 36 |  | 2025-06-26 | 32751 | 2025-05-26 | 2025-06-04 | 36 |  | 2025-06-06 | 32751 |  | 2025-06-10 |  | 2025-06-15 |  | 2025-06-24 | 32751 |  | 2025-07-03 | 32751 |  | 2025-07-14 | 32751 |  | 2025-07-23 | 32751 |  | 2025-08-01 | 32751 |  | 2025-08-12 | 32751 |  | 2025-08-21 |  |  | 2025-09-01 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Palisades South (Debeque) |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
[9 empty] | 2025-04-11 | 2025-04-22 | 2025-04-11 | 2025-05-01 | 67 | 2025-04-30 | 2025-04-25 | 54 | 2025-04-10 | 2025-05-16 | 68 | 2025-05-01 | 2025-06-06 | 53 | 2025-04-22 | 2025-05-27 | 60 | 2025-04-25 | 2025-06-10 | 57 | 2025-04-22 | 2025-05-01 | 60 | 2025-05-05 | 2025-05-05 | 51 |  | 2025-05-07 |  | 2025-05-22 |  | 2025-06-02 | 32751 |  | 2025-06-11 | 32751 | 2025-05-25 | 2025-06-20 | 36 |  | 2025-07-01 | 32751 | 2025-06-01 | 2025-07-10 | 31 | 2025-02-01 | 2025-07-21 | 116 | 2025-02-01 | 2025-07-30 |  | 2025-02-01 | 2025-08-08 | 116 | 2025-02-10 | 2025-02-11 | 111 | 2025-02-13 | 2025-02-20 | 108 | 2025-02-25 | 2025-03-01 | 2025-03-03 | 96 | 2025-03-06 | 2025-03-12 | 93 |  | 2025-07-10 | 32751 | 2025-07-01 | 2025-07-24 | 10 |  |  |  |  | 2025-07-10 | 32751 |  | 2025-07-24 | 32751 | 2025-05-01 | 1900-01-12 | 53 | 2025-05-07 | 1900-01-23 | 49 |  | 2025-02-01 | 1900-02-01 | 116 | 2025-02-06 | 1900-02-15 | 113 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 | 2025-01-05 | 1900-05-02 | 136 | 2025-01-09 | 1900-05-11 | 133 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  | 2025-02-03 | 1900-07-06 | 116 | 2025-02-21 | 1900-07-20 | 102 | 2025-03-11 | 1900-08-03 | 90 | 2025-03-29 | 1900-08-17 | 76 | 2025-04-28 | 1900-09-14 | 56 | 2025-05-07 | 1900-09-21 | 49 | 2025-02-05 | 1900-10-02 | 114 | 2025-02-06 | 1900-10-11 | 113 | 2025-02-08 | 2025-02-15
[9 empty] | 2025-04-10 | 2025-04-20 | 2025-04-12 | 2025-04-29 | 66 | 2025-04-22 | 2025-04-25 | 60 | 2025-04-12 | 2025-05-16 | 66 | 2025-04-23 | 2025-06-06 | 59 | 2025-04-20 | 2025-05-27 | 61 | 2025-04-23 | 2025-06-10 | 59 | 2025-04-20 | 2025-04-29 | 61 | 2025-04-26 | 2025-05-01 | 56 |  | 2025-05-05 |  | 2025-05-05 |  | 2025-05-14 | 32751 |  | 2025-05-23 | 32751 | 2025-05-07 | 2025-06-03 | 49 |  | 2025-06-12 | 32751 | 2025-05-15 | 2025-06-23 | 43 | 2025-01-01 | 2025-07-02 | 139 | 2025-01-03 | 2025-07-11 |  | 2025-01-01 | 2025-07-22 | 139 | 2025-01-04 | 2025-01-10 | 136 | 2025-01-05 | 2025-01-21 | 136 | 2025-01-06 | 2025-01-11 | 2025-01-30 | 131 | 2025-01-05 | 2025-02-10 | 136 |  | 2025-05-09 | 32751 | 2025-04-12 | 2025-05-23 | 66 |  |  |  | 2025-01-03 | 2025-04-22 | 137 | 2025-01-16 | 2025-05-06 | 128 | 2025-04-23 | 1900-01-12 | 59 | 2025-04-28 | 1900-01-23 | 56 |  | 2025-01-03 | 1900-02-01 | 137 | 2025-01-07 | 1900-02-15 | 135 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 | 2025-01-01 | 1900-05-02 | 139 | 2025-01-30 | 1900-05-11 | 118 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  | 2025-01-04 | 1900-07-06 | 136 | 2025-02-01 | 1900-07-20 | 116 | 2025-02-21 | 1900-08-03 | 102 | 2025-02-28 | 1900-08-17 | 97 | 2025-04-09 | 1900-09-14 | 69 | 2025-04-29 | 1900-09-21 | 55 | 2025-01-05 | 1900-10-02 | 136 | 2025-01-08 | 1900-10-11 | 134 | 2025-01-11 | 2025-01-12
| Completed | FL_Pearl Street N11_WIFI |  | Connected Venues |  |  | Tyrone | 205 | 2025-04-12 | 2025-01-31 | 2025-02-15 | 2025-02-11 | 106 | 2025-02-18 | 2025-02-28 | 105 | 2025-02-20 | 2025-03-21 | 103 | 2025-02-28 | 2025-04-11 | 97 | 2025-01-31 | 2025-04-01 | 117 |  | 2025-04-15 | 32751 | 2025-01-31 | 2025-02-11 | 117 | 2025-04-30 | 2025-02-13 | 54 |  | 2025-02-17 |  | 2025-02-10 |  | 2025-02-19 | 32751 |  | 2025-02-28 | 32751 | 2025-02-15 | 2025-03-11 | 106 |  | 2025-03-20 | 32751 | 2025-03-01 | 2025-03-31 | 96 | 2025-03-01 | 2025-04-09 | 96 | 2025-03-03 | 2025-04-18 |  | 2025-03-01 | 2025-04-29 | 96 | 2025-03-13 | 2025-03-11 | 88 | 2025-03-15 | 2025-03-20 | 86 | 2025-03-30 | 2025-04-10 | 2025-03-31 | 68 | 2025-04-01 | 2025-04-09 | 75 |  | 2025-08-05 | 32751 | 2025-08-15 | 2025-08-19 | -25 | C. In progress | Alan B Miller |  | 2025-04-24 | 2025-08-26 | 58 |  | 2025-09-09 | 32751 | 2025-06-01 | 1900-01-12 | 31 | 2025-06-04 | 1900-01-23 | 29 |  | 2025-03-01 | 1900-02-01 | 96 | 2025-03-08 | 1900-02-15 | 91 |  | 1900-03-01 | 32751 | 2024-10-11 | 1900-03-15 | 197 | 2025-05-07 | 1900-03-29 | 49 | 2025-04-01 | 1900-04-09 | 75 | 2024-04-15 | 1900-04-23 | 326 | 2025-05-20 | 1900-05-02 | 40 | 2025-05-21 | 1900-05-11 | 39 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  | 2025-03-01 | 1900-07-06 | 96 | 2025-03-31 | 1900-07-20 | 76 | 2025-04-21 | 1900-08-03 | 61 | 2025-04-26 | 1900-08-17 | 56 | 2025-06-15 | 1900-09-14 | 21 | 2025-06-24 | 1900-09-21 | 15 | 2025-03-01 | 1900-10-02 | 96 | 2025-03-02 | 1900-10-11 | 96 | 2025-03-03 | 2025-03-12
| Completed | Toscana at Valley Ridge |  | Connected Venues |  |  | Christina | 288 | 2025-04-14 | 2025-04-23 | 2025-04-30 | 2025-05-02 | 54 | 2025-05-07 | 2025-05-14 | 49 | 2025-05-08 | 2025-06-04 | 48 | 2025-05-28 | 2025-06-25 | 34 | 2025-04-23 | 2025-06-13 | 59 |  | 2025-06-27 | 32751 | 2025-04-23 | 2025-05-02 | 59 | 2025-05-09 | 2025-05-06 | 47 |  | 2025-05-08 |  | 2025-05-04 |  | 2025-05-13 | 32751 |  | 2025-05-22 | 32751 | 2025-05-05 | 2025-06-02 | 51 |  | 2025-06-11 | 32751 | 2025-06-01 | 2025-06-20 | 31 | 2025-05-01 | 2025-07-01 | 53 | 2025-05-03 | 2025-07-10 |  |  | 2025-07-21 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 | 2025-07-01 | 1900-02-07 | 10 |  | 2025-11-04 | 32751 |  | 2025-11-18 | 32751 |  | Asante-1 |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 | 2025-03-01 | 1900-04-09 | 96 | 2025-03-20 | 1900-04-23 | 83 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | On Hold - No FNE for Now | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
| Completed | Clearview |  | Connected Venues |  |  | Christina | 376 | 2025-04-15 | 2025-04-29 | 2025-05-07 | 2025-05-08 | 49 | 2025-05-10 | 2025-05-21 | 46 | 2025-05-14 | 2025-06-11 | 44 | 2025-05-30 | 2025-07-02 | 32 | 2025-04-29 | 2025-06-20 | 55 |  | 2025-07-04 | 32751 | 2025-04-29 | 2025-05-08 | 55 |  | 2025-05-12 | 32751 |  | 2025-05-14 |  | 2025-05-19 |  | 2025-05-28 | 32751 |  | 2025-06-06 | 32751 | 2025-05-28 | 2025-06-17 | 34 |  | 2025-06-26 | 32751 | 2025-06-28 | 2025-07-07 | 11 |  | 2025-07-16 | 32751 |  | 2025-07-25 |  |  | 2025-08-05 | 32751 |  | 1900-01-09 | 32751 |  | 1899-12-31 | 32751 |  |  | 1900-01-09 | 32751 | 2025-08-01 | 1900-01-18 | -15 |  | 2025-12-05 | 32751 |  | 2025-12-19 | 32751 | FNE | Baptist Parkridge |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45383 | 1900-03-15 | 336 | 2024-10-10 | 1900-03-29 | 198 | 45778 | 1900-04-09 | 53 | 2025-05-20 | 1900-04-23 | 40 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Carrier Add - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
| Completed | Melrose |  | Connected Venues |  |  | Christina | 359 | 2025-04-19 | 2025-04-27 | 2025-05-09 | 2025-05-06 | 47 | 2025-05-20 | 2025-05-23 | 40 | 2025-05-02 | 2025-06-13 | 52 | 2025-05-25 | 2025-07-04 | 36 | 2025-04-27 | 2025-06-24 | 56 |  | 2025-07-08 | 32751 | 2025-04-27 | 2025-05-06 | 56 |  | 2025-05-08 | 32751 |  | 2025-05-12 |  | 2025-05-11 |  | 2025-05-20 | 32751 |  | 2025-05-29 | 32751 |  | 2025-06-09 | 32751 |  | 2025-06-18 | 32751 |  | 2025-06-27 | 32751 |  | 2025-07-08 | 32751 |  | 2025-07-17 |  |  | 2025-07-28 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Debeque Canyon |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Site Mod - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Hold | Completed | OR_Ferguson Rd Quarterra_Wi-Fi |  | Connected Venues |  |  | Ramith | 264 | 2025-04-20 | 2025-04-26 | 2025-05-20 | 2025-05-06 | 40 | 2025-05-30 | 2025-06-03 | 32 | 2025-05-27 | 2025-06-24 | 35 | 2025-06-06 | 2025-07-15 | 27 | 2025-04-26 | 2025-07-03 | 56 |  | 2025-07-17 | 32751 | 2025-04-26 | 2025-05-06 | 56 |  | 2025-05-08 | 32751 |  | 2025-05-12 |  | 2025-05-16 |  | 2025-05-27 | 32751 |  | 2025-06-05 | 32751 |  | 2025-06-16 | 32751 |  | 2025-06-25 | 32751 |  | 2025-07-04 | 32751 |  | 2025-07-15 | 32751 |  | 2025-07-24 |  |  | 2025-08-04 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Debeque Canyon |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Site Mod - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
| Completed | FL Venice Shores Luxury Apartments WIFI |  | Connected Venues |  |  | Tyrone | 293 | 2025-04-22 | 2025-04-25 | 2025-04-30 | 2025-05-06 | 54 | 2025-05-07 | 2025-05-14 | 49 | 2025-05-09 | 2025-06-04 | 47 | 2025-06-07 | 2025-06-25 | 26 | 2025-04-25 | 2025-06-13 | 57 |  | 2025-06-27 | 32751 | 2025-04-25 | 2025-05-06 | 57 |  | 2025-05-08 | 32751 |  | 2025-05-12 |  | 2025-05-13 |  | 2025-05-22 | 32751 |  | 2025-06-02 | 32751 |  | 2025-06-11 | 32751 |  | 2025-06-20 | 32751 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 |  |  | 2025-07-30 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Decatur Hospital |  | 2024-10-09 | 1900-01-09 | 199 | 2025-01-13 | 1900-01-23 | 131 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45736 | 1900-03-15 | 83 | 2025-07-23 | 1900-03-29 | -8 |  | 1900-04-09 | 32751 | 2025-03-28 | 1900-04-23 | 77 |  | 1900-05-02 | 32751 | 2025-05-30 | 1900-05-11 | 32 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Lost | Completed | Waterman RFP |  | Master Communities |  |  | Tyrone | 351 | 2025-04-23 | 2025-04-28 | 2025-05-05 | 2025-05-07 | 51 | 2025-05-08 | 2025-05-19 | 48 | 2025-05-16 | 2025-06-09 | 42 | 2025-06-02 | 2025-06-30 | 31 | 2025-04-28 | 2025-06-18 | 56 |  | 2025-07-02 | 32751 | 2025-04-28 | 2025-05-07 | 56 |  | 2025-05-09 | 32751 |  | 2025-05-13 |  | 2025-05-09 |  | 2025-05-20 | 32751 |  | 2025-05-29 | 32751 |  | 2025-06-09 | 32751 |  | 2025-06-18 | 32751 |  | 2025-06-27 | 32751 |  | 2025-07-08 | 32751 |  | 2025-07-17 |  |  | 2025-07-28 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Health Sciences Research |  | 2024-11-13 | 1900-01-09 | 174 | 2025-04-02 | 1900-01-23 | 74 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45736 | 1900-03-15 | 83 | 2025-07-23 | 1900-03-29 | -8 |  | 1900-04-09 | 32751 | 2025-03-28 | 1900-04-23 | 77 |  | 1900-05-02 | 32751 | 2025-05-30 | 1900-05-11 | 32 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Hold | Completed | Asante Temp Tower 2 |  | DAS |  |  | Ramith | 1 | 2025-04-25 | 2025-04-26 | 2025-05-14 | 2025-05-06 | 44 | 2025-05-27 | 2025-05-28 | 35 | 2025-05-17 | 2025-06-18 | 41 | 2025-06-02 | 2025-07-09 | 31 | 2025-04-26 | 2025-06-27 | 56 |  | 2025-07-11 | 32751 | 2025-04-26 | 2025-05-06 | 56 |  | 2025-05-08 | 32751 |  | 2025-05-12 |  | 2025-05-05 |  | 2025-05-14 | 32751 |  | 2025-05-23 | 32751 |  | 2025-06-03 | 32751 |  | 2025-06-12 | 32751 |  | 2025-06-23 | 32751 |  | 2025-07-02 | 32751 |  | 2025-07-11 |  |  | 2025-07-22 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Long Term Acute Care |  | 2024-11-14 | 1900-01-09 | 173 | 2025-04-01 | 1900-01-23 | 75 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45736 | 1900-03-15 | 83 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 | 2025-03-28 | 1900-04-23 | 77 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
| Completed | IN_McCromicks Greek |  | Connected Venues |  |  | Ramith | 1 | 2025-04-27 | 2025-05-03 | 2025-05-10 | 2025-05-13 | 46 | 2025-05-11 | 2025-05-23 | 46 | 2025-05-17 | 2025-06-13 | 41 | 2025-06-04 | 2025-07-04 | 29 | 2025-05-03 | 2025-06-24 | 51 |  | 2025-07-08 | 32751 | 2025-05-03 | 2025-05-13 | 51 |  | 2025-05-15 | 32751 |  | 2025-05-19 |  | 2025-05-16 |  | 2025-05-27 | 32751 |  | 2025-06-05 | 32751 |  | 2025-06-16 | 32751 |  | 2025-06-25 | 32751 |  | 2025-07-04 | 32751 |  | 2025-07-15 | 32751 |  | 2025-07-24 |  |  | 2025-08-04 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Orthopaedics Hospital |  | 2024-11-14 | 1900-01-09 | 173 | 2025-04-24 | 1900-01-23 | 58 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45736 | 1900-03-15 | 83 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 | 2025-03-28 | 1900-04-23 | 77 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Done | Completed | FL_Waterlin |  | Connected Communities |  |  | Steven | 15000 | 2025-04-28 | 2025-05-06 | 2025-05-20 | 2025-05-15 | 40 | 2025-05-30 | 2025-06-03 | 32 | 2025-05-16 | 2025-06-24 | 42 | 2025-06-03 | 2025-07-15 | 30 | 2025-05-06 | 2025-07-03 | 50 |  | 2025-07-17 | 32751 | 2025-05-06 | 2025-05-15 | 50 |  | 2025-05-19 | 32751 |  | 2025-05-21 |  | 2025-05-23 |  | 2025-06-03 | 32751 |  | 2025-06-12 | 32751 |  | 2025-06-23 | 32751 |  | 2025-07-02 | 32751 |  | 2025-07-11 | 32751 |  | 2025-07-22 | 32751 |  | 2025-07-31 |  |  | 2025-08-11 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Saint Joseph's Hospital |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Done | Completed | TX-Honey Creek |  | Connected Communities |  |  | Steven | 3041 | 2025-04-29 | 2025-05-07 | 2025-05-17 | 2025-05-16 | 41 | 2025-05-30 | 2025-05-30 | 32 | 2025-03-01 | 2025-06-20 | 96 | 2025-04-08 | 2025-07-11 | 70 | 2025-05-07 | 2025-07-01 | 49 | 2025-03-24 | 2025-07-15 | 81 | 2025-05-07 | 2025-05-16 | 49 |  | 2025-05-20 | 32751 |  | 2025-05-22 |  | 2025-05-26 |  | 2025-06-04 | 32751 |  | 2025-06-13 | 32751 |  | 2025-06-24 | 32751 |  | 2025-07-03 | 32751 |  | 2025-07-14 | 32751 |  | 2025-07-23 | 32751 |  | 2025-08-01 |  |  | 2025-08-12 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory University Hospital (Plus A, B, C Clinic - ATT EOL) |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Lost | Completed | Waterman Village |  | Connected Venues |  |  | Tyrone | 350 | 2025-05-01 | 2025-05-09 | 2025-05-26 | 2025-05-20 | 36 | 2025-06-05 | 2025-06-09 | 28 | 2025-05-27 | 2025-06-30 | 35 | 2025-06-16 | 2025-07-21 | 21 | 2025-05-09 | 2025-07-09 | 47 |  | 2025-07-23 | 32751 | 2025-05-09 | 2025-05-20 | 47 |  | 2025-05-22 | 32751 |  | 2025-05-26 |  | 2025-05-29 |  | 2025-06-09 | 32751 |  | 2025-06-18 | 32751 |  | 2025-06-27 | 32751 |  | 2025-07-08 | 32751 |  | 2025-07-17 | 32751 |  | 2025-07-28 | 32751 |  | 2025-08-06 |  |  | 2025-08-15 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Wesley Woods Geriatric Hospital |  | 2024-11-06 | 1900-01-09 | 179 | 2025-04-01 | 1900-01-23 | 75 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45736 | 1900-03-15 | 83 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 | 2025-03-28 | 1900-04-23 | 77 |  | 1900-05-02 | 32751 | 2025-05-30 | 1900-05-11 | 32 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
| Completed | NY_State Street Apartment - Datavalet |  | Connected Venues |  |  | Tyrone | 371 | 2025-05-02 | 2025-05-06 | 2025-03-18 | 2025-05-15 | 85 | 2025-03-24 | 2025-04-01 | 81 | 2025-03-30 | 2025-04-22 | 76 | 2025-04-20 | 2025-05-13 | 61 | 2025-05-06 | 2025-05-01 | 50 |  | 2025-05-15 | 32751 | 2025-05-06 | 2025-05-15 | 50 |  | 2025-05-19 | 32751 |  | 2025-05-21 |  | 2025-05-16 |  | 2025-05-27 | 32751 |  | 2025-06-05 | 32751 |  | 2025-06-16 | 32751 |  | 2025-06-25 | 32751 |  | 2025-07-04 | 32751 |  | 2025-07-15 | 32751 |  | 2025-07-24 |  |  | 2025-08-04 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | FIU |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Hold | On Hold | 707 Terry Coffee Shop |  | Connected Venues |  |  | Christina | 1 | 2025-05-05 |  | 2025-04-01 | 1900-01-09 | 75 | 2025-04-06 | 2025-04-15 | 71 | 2025-04-19 | 2025-05-06 | 61 | 2025-05-10 | 2025-05-27 | 46 | 0 | 2025-05-15 | 32751 |  | 2025-05-29 | 32751 | 0 | 1900-01-09 | 32751 |  | 1900-01-11 | 32751 |  | 1900-01-15 |  |  |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-02-16 | 32751 |  | 1900-02-27 | 32751 |  | 1900-03-08 |  |  | 1900-03-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Glenwood Canyon Backup Power |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Done | On Hold | Glasgow |  | Connected Communities |  |  | Tyrone | 310 | 2025-05-06 | 2025-05-13 | 2025-04-08 | 2025-05-22 | 70 | 2025-04-15 | 2025-04-22 | 65 | 2025-04-08 | 2025-05-13 | 70 | 2025-04-15 | 2025-06-03 | 65 | 2025-05-13 | 2025-05-22 | 45 | 2025-04-22 | 2025-06-05 | 60 | 2025-05-13 | 2025-05-22 | 45 | 2025-04-22 | 2025-05-26 | 60 |  | 2025-05-28 |  | 2025-05-31 |  | 2025-06-10 | 32751 |  | 2025-06-19 | 32751 |  | 2025-06-30 | 32751 |  | 2025-07-09 | 32751 |  | 2025-07-18 | 32751 |  | 2025-07-29 | 32751 |  | 2025-08-07 |  |  | 2025-08-18 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Glenwood Canyon Backup Power |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Lost | Completed | Airabella |  | Connected Communities |  |  | Tyrone | 500 | 2025-05-07 | 2025-05-15 | 2025-04-07 | 2025-05-26 | 71 | 2025-04-15 | 2025-04-21 | 65 | 2025-04-15 | 2025-05-12 | 65 | 2025-04-16 | 2025-06-02 | 64 | 2025-05-15 | 2025-05-21 | 43 | 2025-05-16 | 2025-06-04 | 42 | 2025-05-15 | 2025-05-26 | 43 | 2025-04-22 | 2025-05-28 | 60 |  | 2025-05-30 |  | 2025-05-22 |  | 2025-06-02 | 32751 |  | 2025-06-11 | 32751 |  | 2025-06-20 | 32751 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 |  |  | 2025-08-08 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Hyatt Regency Orlando |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Hold | On Hold | Big Brooke Temp Tower |  | DAS |  |  | Ramith | 1 | 2025-05-11 | 2025-05-27 | 2025-04-11 | 2025-06-05 | 67 | 2025-04-22 | 2025-04-25 | 60 | 2025-04-11 | 2025-05-16 | 67 | 2025-05-04 | 2025-06-06 | 51 | 2025-05-27 | 2025-05-27 | 35 |  | 2025-06-10 | 32751 | 2025-05-27 | 2025-06-05 | 35 |  | 2025-06-09 | 32751 |  | 2025-06-11 |  | 2025-06-02 |  | 2025-06-11 | 32751 |  | 2025-06-20 | 32751 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 | 32751 |  | 2025-08-08 |  |  | 2025-08-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Omni Championsgate Design |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
FM | FM Request | Bermuda Village |  | Connected Venues |  |  | Tyrone | 313 | 2025-05-13 | 2025-05-29 | 2025-04-28 | 2025-06-09 | 56 | 2025-05-06 | 2025-05-12 | 50 | 2025-04-28 | 2025-06-02 | 56 | 2025-05-09 | 2025-06-23 | 47 | 2025-05-29 | 2025-06-11 | 33 | 2025-05-06 | 2025-06-25 | 50 | 2025-05-29 | 2025-06-09 | 33 |  | 2025-06-11 | 32751 |  | 2025-06-13 |  | 2025-06-11 |  | 2025-06-20 | 32751 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 | 32751 |  | 2025-08-08 | 32751 |  | 2025-08-19 |  |  | 2025-08-28 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Packing District: 4Roots |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | Need to Forecast Once GC is Awarded | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Hold | Gathering Requirement | Golden Gem Resi |  | Connected Venues |  |  | Steven | 54 | 2025-05-17 | 2025-06-06 | 2025-04-22 | 2025-06-17 | 60 | 2025-04-29 | 2025-05-06 | 55 | 2025-05-01 | 2025-05-27 | 53 | 2025-05-22 | 2025-06-17 | 38 | 2025-06-06 | 2025-06-05 | 27 | 2025-04-23 | 2025-06-19 | 59 | 2025-06-06 | 2025-06-17 | 27 |  | 2025-06-19 | 32751 |  | 2025-06-23 |  | 2025-06-25 |  | 2025-07-04 | 32751 |  | 2025-07-15 | 32751 |  | 2025-07-24 | 32751 |  | 2025-08-04 | 32751 |  | 2025-08-13 | 32751 |  | 2025-08-22 | 32751 |  | 2025-09-02 |  |  | 2025-09-11 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Parcel B DAS |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | FNE won't be determined until all agreements and contracts are executed | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Network Takeover | On Hold | Bosa REN |  | Connected Venues |  |  | Christina | 457 | 2025-05-18 | 2025-06-08 | 2025-04-01 | 2025-06-17 | 75 | 2025-04-10 | 2025-04-15 | 68 | 2025-05-04 | 2025-05-06 | 51 | 2025-05-24 | 2025-05-27 | 36 | 2025-06-08 | 2025-05-15 | 26 |  | 2025-05-29 | 32751 | 2025-06-08 | 2025-06-17 | 26 |  | 2025-06-19 | 32751 |  | 2025-06-23 |  | 2025-06-25 |  | 2025-07-04 | 32751 |  | 2025-07-15 | 32751 |  | 2025-07-24 | 32751 |  | 2025-08-04 | 32751 |  | 2025-08-13 | 32751 |  | 2025-08-22 | 32751 |  | 2025-09-02 |  |  | 2025-09-11 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Parshall |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
OSP | In Design | Serenade |  | Connected Venues |  |  | Steven | 888 | 2025-05-19 | 2025-06-03 | N/A | 2025-06-12 | #VALUE! | N/A | #VALUE! | #VALUE! | N/A | #VALUE! | #VALUE! | N/A | #VALUE! | #VALUE! | 45811 | #VALUE! | 30 |  | #VALUE! | 32751 | 45811 | 2025-06-12 | 30 |  | 2025-06-16 | 32751 |  | 2025-06-18 |  | 2025-06-20 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 | 32751 |  | 2025-08-08 | 32751 |  | 2025-08-19 | 32751 |  | 2025-08-28 |  |  | 2025-09-08 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | FNE | PH Greer Memorial Hospital |  | 2024-03-14 | 1900-01-09 | 348 | 2024-06-14 | 1900-01-23 | 282 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  | 45583 | 1900-02-01 | 192 | 2025-01-06 | 1900-02-15 | 136 |  | 1900-03-01 | 32751 | 45413 | 1900-03-15 | 314 | 2024-11-01 | 1900-03-29 | 182 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 | 2024-06-10 | 1900-05-11 | 286 | 45607 | 1900-05-25 | 176 | 45742 | 1900-06-22 | 79 |  | 45742 | 1900-07-06 | 79 | 2025-03-26 | 1900-07-20 | 79 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | 45742 | 1900-10-02 | 79 |  | 1900-10-11 | 32751
OSP | In Design | The perle |  | Connected Venues |  |  | Tyrone | 230 | 2025-05-20 | 2025-06-10 | 2025-05-09 | 2025-06-19 | 47 | 2025-05-22 | 2025-05-23 | 38 | 2025-05-09 | 2025-06-13 | 47 | 2025-05-13 | 2025-07-04 | 45 | 2025-06-10 | 2025-06-24 | 25 |  | 2025-07-08 | 32751 | 2025-06-10 | 2025-06-19 | 25 |  | 2025-06-23 | 32751 |  | 2025-06-25 |  | 2025-06-28 |  | 2025-07-08 | 32751 |  | 2025-07-17 | 32751 |  | 2025-07-28 | 32751 |  | 2025-08-06 | 32751 |  | 2025-08-15 | 32751 |  | 2025-08-26 | 32751 |  | 2025-09-04 |  |  | 2025-09-15 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | PH Midlands NE MACC |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45804 | 1900-03-15 | 35 |  | 1900-03-29 | 32751 | 45804 | 1900-04-09 | 35 | 2025-06-11 | 1900-04-23 | 24 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | Need to Forecast Once GC is Awarded | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
OSP | In Design | SBA Jax Data Center |  | Connected Venues |  |  | Ramith | 92 | 2025-05-21 | 2025-06-01 | 2025-05-23 | 2025-06-10 | 37 | 2025-05-31 | 2025-06-06 | 31 | N/A | 2025-06-27 | #VALUE! | N/A | 2025-07-18 | #VALUE! | 45819 | 2025-07-08 | 24 |  | 2025-07-22 | 32751 | 45809 | 2025-06-10 | 31 |  | 2025-06-12 | 32751 |  | 2025-06-16 |  | 2025-06-18 |  | 2025-06-27 | 32751 |  | 2025-07-08 | 32751 |  | 2025-07-17 | 32751 |  | 2025-07-28 | 32751 |  | 2025-08-06 | 32751 |  | 2025-08-15 | 32751 |  | 2025-08-26 |  |  | 2025-09-04 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Prisma Greenville Memorial Hospital |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 44593 | 1900-03-15 | 900 | 2022-08-12 | 1900-03-29 | 762 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | No FNE since this just a maintenance request. | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Design | In Design | The wellinton |  | Connected Venues |  |  | Steven |  | 2025-05-22 | 2025-06-12 | 2025-05-28 | 2025-06-23 | 34 | 2025-05-30 | 2025-06-11 | 32 | 2025-05-28 | 2025-07-02 | 34 | 2025-06-17 | 2025-07-23 | 20 | 2025-06-12 | 2025-07-11 | 23 |  | 2025-07-25 | 32751 | 2025-06-12 | 2025-06-23 | 23 |  | 2025-06-25 | 32751 |  | 2025-06-27 |  | 2025-07-02 |  | 2025-07-11 | 32751 |  | 2025-07-22 | 32751 |  | 2025-07-31 | 32751 |  | 2025-08-11 | 32751 |  | 2025-08-20 | 32751 |  | 2025-08-29 | 32751 |  | 2025-09-09 |  |  | 2025-09-18 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Rancho Springs |  | 2022-03-01 | 1900-01-09 | 880 | 2023-03-07 | 1900-01-23 | 615 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  | 45020 | 1900-02-01 | 595 | 2023-05-09 | 1900-02-15 | 570 |  | 1900-03-01 | 32751 | 45536 | 1900-03-15 | 226 | 2024-02-27 | 1900-03-29 | 360 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 | 2024-09-13 | 1900-05-11 | 217 | 45211 | 1900-05-25 | 458 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
OSP | In Design | 37 Tree view |  | Connected Venues |  |  | Tyrone | 300 | 2025-05-23 | 2025-06-08 | 2025-05-29 | 2025-06-17 | 33 | 2025-06-02 | 2025-06-12 | 31 | 2025-05-29 | 2025-07-03 | 33 | 2025-06-20 | 2025-07-24 | 17 | 2025-06-08 | 2025-07-14 | 26 |  | 2025-07-28 | 32751 | 2025-06-08 | 2025-06-17 | 26 |  | 2025-06-19 | 32751 |  | 2025-06-23 |  | 2025-06-09 |  | 2025-06-18 | 32751 |  | 2025-06-27 | 32751 |  | 2025-07-08 | 32751 |  | 2025-07-17 | 32751 |  | 2025-07-28 | 32751 |  | 2025-08-06 | 32751 |  | 2025-08-15 |  |  | 2025-08-26 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Richland Hospital |  | 2024-09-18 | 1900-01-09 | 214 | 2025-01-13 | 1900-01-23 | 131 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  | 45562 | 1900-02-01 | 207 | 2024-12-05 | 1900-02-15 | 158 |  | 1900-03-01 | 32751 | 45536 | 1900-03-15 | 226 | 2025-02-17 | 1900-03-29 | 106 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 | 2024-10-01 | 1900-05-11 | 205 | 45544 | 1900-05-25 | 221 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Network Takeover | In Design | Prisma Health ¦ Blount Memorial Hospital |  | DAS |  |  | Adam | 6 Floors | 2025-05-24 | 2025-06-04 | N/A | 2025-06-13 | #VALUE! |  | #VALUE! | 32751 |  | #VALUE! | 32751 |  | #VALUE! | 32751 | 45812 | #VALUE! | 29 |  | #VALUE! | 32751 | 45812 | 2025-06-13 | 29 |  | 2025-06-17 | 32751 |  | 2025-06-19 |  | 2025-06-20 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 | 32751 |  | 2025-08-08 | 32751 |  | 2025-08-19 | 32751 |  | 2025-08-28 |  |  | 2025-09-08 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | St. Charles Convention Center and Hotel |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
| Gathering Requirement | Veridea |  | Connected Communities |  |  | Steven |  | 2025-05-25 | 2025-06-15 | 2025-06-18 | 2025-06-24 | 19 | 2025-06-29 | 2025-07-02 | 11 | 2025-07-01 | 2025-07-23 | 10 | 2025-06-01 | 2025-08-13 | 31 | 2025-06-15 | 2025-08-01 | 21 |  | 2025-08-15 | 32751 | 2025-06-15 | 2025-06-24 | 21 |  | 2025-06-26 | 32751 |  | 2025-06-30 |  | 2025-07-01 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 | 32751 |  | 2025-08-08 | 32751 |  | 2025-08-19 | 32751 |  | 2025-08-28 | 32751 |  | 2025-09-08 |  |  | 2025-09-17 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | State of Michigan Capitol Campus |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 44166 | 1900-03-15 | 1205 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 | 44410 | 1900-05-25 | 1031 | 44734 | 1900-06-22 | 799 |  | 44734 | 1900-07-06 | 799 | 2022-06-22 | 1900-07-20 | 799 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Radio Swap - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
| Completed | West Jefferson Medical Center Enterprise DAS |  | DAS |  |  | Benson | 419 | 2025-04-13 | 2025-04-23 | 2025-04-29 | 2025-05-02 | 55 | 2025-05-04 | 2025-05-13 | 51 | 2025-05-03 | 2025-06-03 | 51 | 2025-05-30 | 2025-06-24 | 32 | 2025-04-23 | 2025-06-12 | 59 |  | 2025-06-26 | 32751 | 2025-04-23 | 2025-05-02 | 59 | 2025-05-02 | 2025-05-06 | 52 |  | 2025-05-08 |  | 2025-05-23 |  | 2025-06-03 | 32751 |  | 2025-06-12 | 32751 | 2025-05-26 | 2025-06-23 | 36 |  | 2025-07-02 | 32751 | 2025-06-20 | 2025-07-11 | 17 | 2024-04-01 | 2025-07-22 | 336 | 2025-04-03 | 2025-07-31 |  | 2025-04-01 | 2025-08-11 | 75 | 2025-04-09 | 2025-04-10 | 69 | 2025-04-10 | 2025-04-21 | 68 | 2025-04-30 | 2025-05-09 | 2025-04-30 | 47 | 2025-05-10 | 2025-05-09 | 46 |  | 2025-09-12 | 32751 | 2025-10-14 | 2025-09-26 | -67 |  | Asante Temp Tower #2 |  |  | 2025-10-23 | 32751 |  | 2025-11-06 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 | 2025-01-03 | 1900-04-09 | 137 | 2025-02-01 | 1900-04-23 | 116 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  | 2025-04-02 | 1900-07-06 | 74 | 2025-05-02 | 1900-07-20 | 52 | 2025-05-21 | 1900-08-03 | 39 | 2025-06-20 | 1900-08-17 | 17 | 2025-07-31 | 1900-09-14 | -14 | 2025-08-03 | 1900-09-21 | -15 | On Hold - No FNE for Now | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
| Completed | Enclave on Golden Triangle |  | Connected Venues |  |  | Christina | 273 | 2025-04-16 | 2025-04-27 | 2025-05-08 | 2025-05-06 | 48 | 2025-05-14 | 2025-05-22 | 44 | 2025-05-13 | 2025-06-12 | 45 | 2025-06-01 | 2025-07-03 | 31 | 2025-04-27 | 2025-06-23 | 56 |  | 2025-07-07 | 32751 | 2025-04-27 | 2025-05-06 | 56 |  | 2025-05-08 | 32751 |  | 2025-05-12 |  | 2025-05-27 |  | 2025-06-05 | 32751 |  | 2025-06-16 | 32751 | 2025-07-01 | 2025-06-25 | 10 |  | 2025-07-04 | 32751 | 2025-07-02 | 2025-07-15 | 9 | 2025-08-01 | 2025-07-24 | -15 | 2025-08-02 | 2025-08-04 |  |  | 2025-08-13 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 | 2025-04-01 | 1900-02-07 | 75 |  | 2025-08-05 | 32751 |  | 2025-08-19 | 32751 | C. Design | Belle Isle Phase 2 |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 44378 | 1900-03-15 | 1053 | 2022-08-25 | 1900-03-29 | 753 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | Need to Forecast Once GC is Awarded | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
| Completed | Walmart Enterprise DAS |  | DAS |  |  | Steven | N/A | 2025-04-21 | 2025-04-29 | 2025-05-11 | 2025-05-08 | 46 | 2025-05-24 | 2025-05-23 | 36 | 2025-05-18 | 2025-06-13 | 41 | 2025-05-31 | 2025-07-04 | 31 | 2025-04-29 | 2025-06-24 | 55 |  | 2025-07-08 | 32751 | 2025-04-29 | 2025-05-08 | 55 |  | 2025-05-12 | 32751 |  | 2025-05-14 |  | 2025-05-29 |  | 2025-06-09 | 32751 |  | 2025-06-18 | 32751 |  | 2025-06-27 | 32751 |  | 2025-07-08 | 32751 |  | 2025-07-17 | 32751 |  | 2025-07-28 | 32751 |  | 2025-08-06 |  |  | 2025-08-15 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Dr Phillips Center |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 44470 | 1900-03-15 | 987 | 2023-12-07 | 1900-03-29 | 418 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Carrier Add - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
Hold | Completed | Romano Capital - WA_Palisade_NC |  | Connected Communities |  |  | Barrett/Christina | 450 | 2025-04-24 | 2025-05-02 | 2025-05-10 | 2025-05-13 | 46 | 2025-05-22 | 2025-05-23 | 38 | 2025-04-01 | 2025-06-13 | 75 | 2025-04-17 | 2025-07-04 | 63 | 2025-05-02 | 2025-06-24 | 52 |  | 2025-07-08 | 32751 | 2025-05-02 | 2025-05-13 | 52 |  | 2025-05-15 | 32751 |  | 2025-05-19 |  | 2025-06-02 |  | 2025-06-11 | 32751 |  | 2025-06-20 | 32751 |  | 2025-07-01 | 32751 |  | 2025-07-10 | 32751 |  | 2025-07-21 | 32751 |  | 2025-07-30 | 32751 |  | 2025-08-08 |  |  | 2025-08-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | Emory Hillandale Hospital |  | 2024-11-15 | 1900-01-09 | 172 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45736 | 1900-03-15 | 83 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 | 2025-03-28 | 1900-04-23 | 77 |  | 1900-05-02 | 32751 | 2025-05-30 | 1900-05-11 | 32 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
| Completed | Heights at Meridian |  | Connected Venues |  |  | Christina | 339 | 2025-04-17 | 2025-05-04 | 2025-05-10 | 2025-05-13 | 46 | 2025-05-21 | 2025-05-23 | 39 | 2025-05-16 | 2025-06-13 | 42 | 2025-06-03 | 2025-07-04 | 30 | 2025-05-04 | 2025-06-24 | 51 |  | 2025-07-08 | 32751 | 2025-05-04 | 2025-05-13 | 51 |  | 2025-05-15 | 32751 |  | 2025-05-19 |  | 2025-05-30 |  | 2025-06-10 | 32751 |  | 2025-06-19 | 32751 |  | 2025-06-30 | 32751 |  | 2025-07-09 | 32751 |  | 2025-07-18 | 32751 |  | 2025-07-29 | 32751 |  | 2025-08-07 |  |  | 2025-08-18 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 | 2025-02-03 | 1900-02-07 | 116 |  | 2025-06-09 | 32751 |  | 2025-06-23 | 32751 | FNE | Cedar Hill Medical |  | 2024-09-09 | 1900-01-09 | 221 | 2025-01-13 | 1900-01-23 | 131 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 | 45597 | 45597 | 1900-02-01 | 182 | 2024-11-01 | 1900-02-15 | 182 |  | 1900-03-01 | 32751 | 45576 | 1900-03-15 | 197 | 2025-01-08 | 1900-03-29 | 134 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 | 2025-01-06 | 1900-05-11 | 136 | 45670 | 1900-05-25 | 131 | 45744 | 1900-06-22 | 77 |  | 45744 | 1900-07-06 | 77 | 2025-03-28 | 1900-07-20 | 77 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | 2025-04-25 | 1900-10-02 | 57 |  | 1900-10-11 | 32751
Done | Completed | RS Apartments_Retrofit_GPON |  | Connected Venues |  |  | Ramith | 306 | 2025-05-15 | 2025-05-27 | 2025-04-29 | 2025-06-05 | 55 | 2025-05-05 | 2025-05-13 | 51 | 2025-04-29 | 2025-06-03 | 55 | 2025-05-19 | 2025-06-24 | 41 | 2025-05-27 | 2025-06-12 | 35 | 2025-05-14 | 2025-06-26 | 44 | 2025-05-27 | 2025-06-05 | 35 | 2025-05-23 | 2025-06-09 | 37 |  | 2025-06-11 |  | 2025-06-23 |  | 2025-07-02 | 32751 |  | 2025-07-11 | 32751 |  | 2025-07-22 | 32751 |  | 2025-07-31 | 32751 |  | 2025-08-11 | 32751 |  | 2025-08-20 | 32751 |  | 2025-08-29 |  |  | 2025-09-09 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Packing District: Momentic Studios ORPD LLC |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | Need to Forecast Once GC is Awarded | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
[12 empty] | 1900-01-09 | 32751 |  | 1900-01-12 | 32751 |  | 1900-02-02 | 32751 |  | 1900-02-23 | 32751 | 0 | 1900-02-13 | 32751 |  | 1900-02-27 | 32751 | 0 | 1900-01-09 | 32751 |  | 1900-01-11 | 32751 |  | 1900-01-15 |  |  |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-02-16 | 32751 |  | 1900-02-27 | 32751 |  | 1900-03-08 |  |  | 1900-03-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. Design | The Cliffs at Walnut Cove |  | 2025-02-24 | 1900-01-09 | 101 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 | 45659 | 1900-03-15 | 138 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
[12 empty] | 1900-01-09 | 32751 |  | 1900-01-12 | 32751 |  | 1900-02-02 | 32751 |  | 1900-02-23 | 32751 | 0 | 1900-02-13 | 32751 |  | 1900-02-27 | 32751 | 0 | 1900-01-09 | 32751 |  | 1900-01-11 | 32751 |  | 1900-01-15 |  |  |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-02-16 | 32751 |  | 1900-02-27 | 32751 |  | 1900-03-08 |  |  | 1900-03-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 |  | Valley of Wildflower (Temp Tower #3) |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | On Hold - No FNE for Now | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
[12 empty] | 1900-01-09 | 32751 |  | 1900-01-12 | 32751 |  | 1900-02-02 | 32751 |  | 1900-02-23 | 32751 | 0 | 1900-02-13 | 32751 |  | 1900-02-27 | 32751 | 0 | 1900-01-09 | 32751 |  | 1900-01-11 | 32751 |  | 1900-01-15 |  |  |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-02-16 | 32751 |  | 1900-02-27 | 32751 |  | 1900-03-08 |  |  | 1900-03-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | West Henderson |  | 2024-10-22 | 1900-01-09 | 190 | 2024-12-27 | 1900-01-23 | 142 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  | 45580 | 1900-02-01 | 195 | 2024-11-12 | 1900-02-15 | 175 |  | 1900-03-01 | 32751 | 45536 | 1900-03-15 | 226 | 2024-12-12 | 1900-03-29 | 153 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 | 2024-10-21 | 1900-05-11 | 191 | 45600 | 1900-05-25 | 181 | 45639 | 1900-06-22 | 152 |  | 45639 | 1900-07-06 | 152 | 2024-12-13 | 1900-07-20 | 152 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 | DAS Site Mod - No FNE | 1900-10-02 | #VALUE! |  | 1900-10-11 | 32751
[12 empty] | 1900-01-09 | 32751 |  | 1900-01-12 | 32751 |  | 1900-02-02 | 32751 |  | 1900-02-23 | 32751 | 0 | 1900-02-13 | 32751 |  | 1900-02-27 | 32751 | 0 | 1900-01-09 | 32751 |  | 1900-01-11 | 32751 |  | 1900-01-15 |  |  |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-02-16 | 32751 |  | 1900-02-27 | 32751 |  | 1900-03-08 |  |  | 1900-03-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 | C. In progress | Westgate Mall |  | 2024-01-17 | 1900-01-09 | 389 | 2024-04-12 | 1900-01-23 | 327 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  | 45441 | 1900-02-01 | 294 | 2024-07-02 | 1900-02-15 | 270 |  | 1900-03-01 | 32751 | 45730 | 1900-03-15 | 87 | 2025-01-15 | 1900-03-29 | 129 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 | 2024-09-03 | 1900-05-11 | 225 | 45685 | 1900-05-25 | 120 | 45769 | 1900-06-22 | 60 |  | 45769 | 1900-07-06 | 60 | 2025-04-22 | 1900-07-20 | 60 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
[12 empty] | 1900-01-09 | 32751 |  | 1900-01-12 | 32751 |  | 1900-02-02 | 32751 |  | 1900-02-23 | 32751 | 0 | 1900-02-13 | 32751 |  | 1900-02-27 | 32751 | 0 | 1900-01-09 | 32751 |  | 1900-01-11 | 32751 |  | 1900-01-15 |  |  |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-02-16 | 32751 |  | 1900-02-27 | 32751 |  | 1900-03-08 |  |  | 1900-03-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 |  |  |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
[12 empty] | 1900-01-09 | 32751 |  | 1900-01-12 | 32751 |  | 1900-02-02 | 32751 |  | 1900-02-23 | 32751 | 0 | 1900-02-13 | 32751 |  | 1900-02-27 | 32751 | 0 | 1900-01-09 | 32751 |  | 1900-01-11 | 32751 |  | 1900-01-15 |  |  |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-02-16 | 32751 |  | 1900-02-27 | 32751 |  | 1900-03-08 |  |  | 1900-03-19 | 32751 |  | 1900-01-09 | 32751 |  | 1900-01-18 | 32751 |  |  | 1900-01-29 | 32751 |  | 1900-02-07 | 32751 |  | 1900-05-04 | 32751 |  | 1900-05-18 | 32751 |  |  |  |  | 1900-01-09 | 32751 |  | 1900-01-23 | 32751 |  | 1900-01-12 | 32751 |  | 1900-01-23 | 32751 |  |  | 1900-02-01 | 32751 |  | 1900-02-15 | 32751 |  | 1900-03-01 | 32751 |  | 1900-03-15 | 32751 |  | 1900-03-29 | 32751 |  | 1900-04-09 | 32751 |  | 1900-04-23 | 32751 |  | 1900-05-02 | 32751 |  | 1900-05-11 | 32751 |  | 1900-05-25 | 32751 |  | 1900-06-22 | 32751 |  |  | 1900-07-06 | 32751 |  | 1900-07-20 | 32751 |  | 1900-08-03 | 32751 |  | 1900-08-17 | 32751 |  | 1900-09-14 | 32751 |  | 1900-09-21 | 32751 |  | 1900-10-02 | 32751 |  | 1900-10-11 | 32751
Total | [7 empty] | 42 | 46 |  |  |  |  | 44 | [5 empty] | 43 | [5 empty] | 15 | [5 empty] | 11 | [18 empty] | 7 | [5 empty] | 6 | [5 empty] | 5 |  |  | 5 |  |  | 5 | 4 | [5 empty] | 0 |  |  | 4 | [8 empty] | 12 | [5 empty] | 3 | [6 empty] | 9 | [8 empty] | 13 | [5 empty] | 13 | [5 empty] | 15 | [12 empty] | 10 |  |  | 4 |  |  | 4 |  |  | 4 |  |  | 4 | [5 empty] | 3 |  |  | 3 | 3
Formulas:
ROM Request Forecast = WORKDAY(Table2[[#This Row],[Kickoff date]], 7)
Days Passed Since ROM Request = NETWORKDAYS(Table2[[#This Row],[ROM Request]], TODAY())
ROM Receive Forecast = WORKDAY(Table2[[#This Row],[ROM Request]], 10)
Days Passed Since ROM Received = NETWORKDAYS(Table2[[#This Row],[ROM Receive]], TODAY())
Backhaul Cost Request Forecast = WORKDAY(Table2[[#This Row],[ROM Receive Forecast]], 15)
Days Since BC Request = NETWORKDAYS(Table2[[#This Row],[Backhaul Cost Request]], TODAY())
Backhaul Cost Receive Forecast = WORKDAY(Table2[[#This Row],[Backhaul Cost Request Forecast]], 15)
Days Since BC Received = NETWORKDAYS(Table2[[#This Row],[Backhaul Cost Receive]], TODAY())
Ricardy = Table2[[#This Row],[Kickoff date]]
Ricardy = [Email]+10
OSP Request Forecast = WORKDAY(Table2[[#This Row],[Backhaul Cost Request Forecast]], 7)
Days Since OSP Request = NETWORKDAYS(Table2[[#This Row],[OSP Request]], TODAY())
OSP Receive Forecast = WORKDAY(Table2[[#This Row],[OSP Request Forecast]], 10)
Days Since OSP Received = NETWORKDAYS(Table2[[#This Row],[OSP Receive]], TODAY())
FM Request Forecast = WORKDAY(Table2[[#This Row],[Kickoff date]], 7)
Days Since FM Request = NETWORKDAYS(Table2[[#This Row],[FM Request]], TODAY())
FM Receive Forecast = WORKDAY(Table2[[#This Row],[FM Request Forecast ]], 2)
Days Since FM Received = NETWORKDAYS(Table2[[#This Row],[FM receive]], TODAY())
FM Review Forecast = WORKDAY(Table2[[#This Row],[FM Receive Forecast ]], 2)
Proposal Acceptance Forecast = WORKDAY(Table2[[#This Row],[1-pager Submission to BD]], 7)
Firm Pricing Request Forecast = WORKDAY(Table2[[#This Row],[Proposal Acceptance Forecast]], 7)
Days Since Firm Pricing Request = NETWORKDAYS(Table2[[#This Row],[Firm Pricing request]], TODAY())
Site Walk Forecast = WORKDAY(Table2[[#This Row],[Firm Pricing Request Forecast]], 7)
Days Since Site Walk = NETWORKDAYS(Table2[[#This Row],[Site Walk]], TODAY())
Firm Quote Receival Forecast = WORKDAY(Table2[[#This Row],[Site Walk Forecast]], 7)
Days Since Firm Quote Receival = NETWORKDAYS(Table2[[#This Row],[Firm Quote Receival]], TODAY())
Final Design & BOM Forecast = WORKDAY(Table2[[#This Row],[Firm Quote Receival Forecast ]], 7)
Days Since Final Design & BOM = NETWORKDAYS(Table2[[#This Row],[Final Design & BOM(20 calendar days from site walk)]], TODAY())
FM Request 2 Forecast = WORKDAY(Table2[[#This Row],[Final Design & BOM Forecast ]], 7)
Days Since FM Request 2 = NETWORKDAYS(Table2[[#This Row],[FM Request 2]], TODAY())
FM Review 2 Forecast = WORKDAY(Table2[[#This Row],[FM Request 2 Forecast]], 7)
Tax Review Forecast = WORKDAY(Table2[[#This Row],[FM Review 2 Forecast]], 7)
Days Since Tax Review = NETWORKDAYS(Table2[[#This Row],[Tax Review]], TODAY())
Tax Approval Forecast = WORKDAY(Table2[[#This Row],[Tax Review]], 7)
Days Since Tax Approval = NETWORKDAYS(Table2[[#This Row],[Tax Approval]], TODAY())
Final Proposal Submission Forecast = WORKDAY(Table2[[#This Row],[Tax Approval Forecast]], 7)
Days Since Final Proposal Submission = NETWORKDAYS(Table2[[#This Row],[Final proposal submission]], TODAY())
BD Submits Proposal Forecast = WORKDAY(Table2[[#This Row],[Final Proposal Submission Forecast]], 7)
Days Since BD Submitted Proposal = NETWORKDAYS(Table2[[#This Row],[BD submits proposal]], TODAY())
Final Proposal Acceptance Forecast = WORKDAY(Table2[[#This Row],[BD Submits Proposal Forecast]], 7)
Days Since Final Proposal Accepted = NETWORKDAYS(Table2[[#This Row],[Final Proposal Accepted]], TODAY())
Legal Agreement Forecast = WORKDAY(Table2[[#This Row],[Final Proposal Accepted]], 90)
Days Since Legal Agreement = NETWORKDAYS(Table2[[#This Row],[Legal Agreement]], TODAY())
Executed Agreement Forecast = WORKDAY(Table2[[#This Row],[Legal Agreement Forecast]], 10)
Days Since Executed Agreement = NETWORKDAYS(Table2[[#This Row],[Executed Agreement]], TODAY())
A&E Request Forecast = WORKDAY(Table2[[#This Row],[Executed Agreement]], 7)
Days Since A&E Request = NETWORKDAYS(Table2[[#This Row],[A&E Request]], TODAY())
A&E Receive Forecast = WORKDAY(Table2[[#This Row],[A&E Request Forecast]], 10)
Days Since A&E Receive = NETWORKDAYS(Table2[[#This Row],[A&E receive]], TODAY())
Budget Request Forecast = WORKDAY(Table2[[#This Row],[FM Approval meeting ]], 10)
Days Since Budget Request = NETWORKDAYS(Table2[[#This Row],[Budget Request]], TODAY())
Budget Approval Forecast = WORKDAY(Table2[[#This Row],[Budget Request Forecast]], 7)
Days Since Budget Approval = NETWORKDAYS(Table2[[#This Row],[Budget Approval]], TODAY())
PO Request for OEM Forecast = WORKDAY(Table2[[#This Row],[Budget Approval Forecast ]], 7)
Days Since PO Request for OEM = NETWORKDAYS(Table2[[#This Row],[PO Request for OEM ]], TODAY())
PO Approval Forecast = WORKDAY(Table2[[#This Row],[PO Request for OEM Forecast]], 10)
Days Since PO Approval = NETWORKDAYS(Table2[[#This Row],[PO Approval]], TODAY())
Backhaul Order Forecast = WORKDAY(Table2[[#This Row],[PO Approval Forecast]], 10)
Days Since Backhaul Order = NETWORKDAYS(Table2[[#This Row],[backhaul ordered]], TODAY())
RTP Request Forecast = WORKDAY(Table2[[#This Row],[Backhaul Order Forecast]], 10)
Days Since RTP Request = NETWORKDAYS(Table2[[#This Row],[RTP Request]], TODAY())
RTP Approval Forecast = WORKDAY(Table2[[#This Row],[RTP Request Forecast]], 10)
Days Since RTP Approval = NETWORKDAYS(Table2[[#This Row],[RTP Approved]], TODAY())
RFP Request Forecast = WORKDAY(Table2[[#This Row],[RTP Approval Forecast ]], 7)
Days Since RFP Request = NETWORKDAYS(Table2[[#This Row],[RFP Request]], TODAY())
RFP Received Forecast = WORKDAY(Table2[[#This Row],[RFP Request Forecast ]], 10)
Days Since RFP Received = NETWORKDAYS(Table2[[#This Row],[RFP Received]], TODAY())
PO for GC Request Forecast = WORKDAY(Table2[[#This Row],[RFP Received Forecast ]], 7)
Days Since PO for GC Request = NETWORKDAYS(Table2[[#This Row],[PO for GC Request]], TODAY())
PO for GC Approval Forecast = WORKDAY(Table2[[#This Row],[PO for GC Request Forecast ]], 7)
Days Since PO for GC Approval = NETWORKDAYS(Table2[[#This Row],[PO for GC Approved]], TODAY())
Construction Start Forecast = WORKDAY(Table2[[#This Row],[PO for GC Approval Forecast ]], 10)
Days Since Construction Start = NETWORKDAYS(Table2[[#This Row],[Construction Start]], TODAY())
Construction Complete Forecast = WORKDAY(Table2[[#This Row],[Construction Start Forecast ]], 20)
Days Since Construction Complete = NETWORKDAYS(Table2[[#This Row],[Construction Complete]], TODAY())
Integration Start Forecast = WORKDAY(Table2[[#This Row],[Construction Complete Forecast ]], 10)
Days Since Integration Start = NETWORKDAYS(Table2[[#This Row],[Integration Start]], TODAY())
Integration Complete Forecast = WORKDAY(Table2[[#This Row],[Integration Start Forecast ]], 10)
Days Since Integration Complete = NETWORKDAYS(Table2[[#This Row],[Integration Complete]], TODAY())
Close Out Package Forecast = WORKDAY(Table2[[#This Row],[Integration Complete Forecast ]], 10)
Days Since Close Out Package = NETWORKDAYS(Table2[[#This Row],[Close Out Package(2weeks from integration complete]], TODAY())
Acceptance Testing Forecast = WORKDAY(Table2[[#This Row],[Close Out Package Forecast ]], 10)
Days Since Acceptance Testing = NETWORKDAYS(Table2[[#This Row],[Acceptance testing 2 weeks from close out package)]], TODAY())
Customer Acceptance Forecast = WORKDAY(Table2[[#This Row],[Acceptance Testing Forecast ]], 20)
Days Since Customer Acceptance = NETWORKDAYS(Table2[[#This Row],[Customer acceptance(1 month after acceptance testing)]], TODAY())
Operations Handoff Forecast = WORKDAY(Table2[[#This Row],[Customer Acceptance Forecast ]], 5)
Days Since Operations Handoff = NETWORKDAYS(Table2[[#This Row],[Operations handoff(1 week after customer acceptance)]], TODAY())
FNE Date Forecast = WORKDAY(Table2[[#This Row],[Operations Handoff Forecast ]], 7)
Days Since FNE Date = NETWORKDAYS(Table2[[#This Row],[FNE Date]], TODAY())
FNE Notice Forecast = WORKDAY(Table2[[#This Row],[FNE Date Forecast ]], 7)
Days Since FNE Notice = NETWORKDAYS(Table2[[#This Row],[FNE Notice]], TODAY())
Days Since Proposal Accepted = IF(ISBLANK(Table2[[#This Row],[Firm Pricing request]]), NETWORKDAYS(Table2[[#This Row],[Proposal Accepted]], TODAY()), NETWORKDAYS(Table2[[#This Row],[Proposal Accepted]], Table2[[#This Row],[Firm Pricing request]]))
Integration Complete = [Integration Start]+18
FNE Notice = [FNE Date]+1
PMDB Update = [FNE Notice]+2
Revenue Billing(PMDB) = [FNE Notice]+9
RFP Received = [RFP Request]+19
RTP Approved = [RTP Request]+125

## New
Opportunity to Agreement (Pre-Sales) | [89 empty] | Sales | [20 empty] | Construction
Pricing | [62 empty] | Proposal | [17 empty] | Legal Agreement | [8 empty] | Planning | [20 empty] | Execution | [18 empty] | Closing
Sales (BD) | Sales(BD) | Sales(BD) |  |  | Sales(BD) |  |  | Sales(BD) |  |  | Sales Operations |  |  | Sales Operations | Sales Operations | Sales Operations | Sales Operations | Sales Operations | Sales Operations |  | Sales Operations |  |  | Sales Operations |  |  | Sales Operation |  |  | Network Engineering & Design |  |  | Network Engineering & Design |  |  | Construction |  |  | Sales Operation |  |  | Sales Operations |  |  | Finance/M&A |  |  | Tax |  |  | Sales Operations |  |  | Sales(BD) |  |  | Sales(BD) |  |  | Sales Operations |  |  | Sales Operations |  |  | Sales Operations |  |  | Sales(BD) |  |  | Sales Operations |  |  | Sales(BD) |  |  | Sales(BD) |  |  | Sales(BD) |  |  | Legal |  |  | Legal |  |  | Sales Operations |  |  | Construtcion |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Construction |  |  | Network Engineering & Design |  |  | Network Engineering & Design |  |  | Network Engineering & Design |  |  | Construction |  |  | Construction | QC/Safety |  |  | Network Engineering & Design |  |  | Construction |  |  | Network Operations |  |  | Construction
BD creates opportunity in CRM | BD Name | Conduct meeting/call to explore opportunity | Explore Opportunity Forecast | Days Passed Since Opportunity Explored | Prospect Interested in proposal | Date of Prospect Interest | Days Passed Since Prospect Interest Confirmed | BD submits email to NSE Design Distro | BD Submission to Design Distro Forecast | Days Passed Since BD Submission to Design Distro | Program Manager adds request to tracker | Tracker Update Forecast | Days Passed Since Tracker Updated | Request is MDU? | Opp Name | Opp ID | Deal Type | Property Type | #Units | SBA or Aerwave | P.M Check with BD OK to submit Aerwave | PM Check-in Forecast | Days Passed Since PM Check-in | P.M Submit Request to Aerwave | PM Submission to Aerwave Forecast | Days Passed Since PM Submission to Aerwave | Program Manager schedules kickoff call to assign action Items & align timelines Est. 2 days | Program Manager Kickoff Forecast | Days Passed Since Program Manager Kickoff | Backhaul pricing Est. 15 days | Backhaul Pricing Forecast | Days Passed Since Backhaul Pricing | Design, ROM (Est. 10 days) | Design, ROM Forecast | Days Passed Since Design, ROM | OSP Pricing (Est. 10 days) | OSP Pricing Forecast | Days Passed Since OSP Pricing | Fin Analyst creates fin. model | Financial Model Creation Forecast | Days Passed Since Financial Model Creation | Sales Ops Peer review (Est. 7 days) | Sales Ops Peer Review Forecast | Days Passed Since Sales Ops Review | Finance Peer review (Est. 7 days) | Finance Peer Review Forecast | Days Passed Since Finance Peer Review | Tax fin. model review (Est. 2 days) | Tax Financial Model Review Forecast | Days Passed Since Tax Fin. Model Review | Program Manager Submits Fin. Model to BD for Review (Est. 2 days) | Program Manager Submits Fin. Model to BD Forecast | Days Passed Since Program Manager submits fin. model to BD | BD reviews Fin. Model Pricing | BD Review Forecast | Days Passed Since BD Reviewed Fin. Model | BD Responds OK to Move Forward | BD Responds to Move Forward Forecast | Days Passed Since BD Responds to Move Forward | Program Manager validates with appropriate teams the pricing data inputs (Est. 2 days) | Program Manager Validation Forecast | Days Passed Since Program Manager Validation | Program Manager creates 1 pager proposal (Est. 2 days) | 1-Pager Proposal Forecast | Days Passed Since Program Manager Creates 1-Pager Proposal | Program Manager creates full proposal (Est. 10 days) | Full Proposal Forecast | Days Since Full Proposal | BD submits proposal | BD Submits Proposal Forecast | Days Passed Since BD Submits Proposal | M. Director Presents to CAC (Est. 10 days) | M. Director Presents to CAC Forecast | Days Passed Since M. Director Presents to CAC | Proposal Accepted? | Proposal Acceptance Date | Days Since Proposal Accepted | Update record in CRM | CRM Update Forecast | Days Passed Since CRM Update | Liaison/review redlines | Liason/Review Redlines Forecast | Days Passed Passed Since Liason/Review Redlines | Draft Agreement (Est. 90 days) | Draft Agreement Forecast | Days Passed Since Agreement Drafted | Executed Agreement (10 days) | Agreement Execution Forecast | Days Passed Since Agreement Executed | Prog Manager schedules Kick-off meeting (Est. 3 days) | Kickoff Meeting Forecast | Days Passed Since Kickoff Meeting | Budget Approvals (Est. 7 days) | Budget Approval Forecast | Days Passed Since Budget Approval | Order backhaul (Est. 7 days) | Backhaul Order Forecast | Days Passed Since Backhaul Ordered | Quotes updates if changes in BOM list (Est. 7 days) | Quote Update Forecast | Days Passed Since Quote Updated | Final BOM (Est. 7 days) | Final BOM Forecast | Days Passed Since Final BOM | Submit POs (Est. 7 days) | PO Submission Forecast | Days Passed Since PO Submission | RTP | RTP Forecast | Days Since RTP Received | Coordinate materials logistics (Est. 8 weeks) | Materials Logistic Coordination Completion Forecast | Days Passed Since Materials Logistics Coordination Completion | Monitor Construction Start (Est. 6 months) | Construction Start Forecast | Days Passed Since Construction Start | Core switches configuration (Est. 2 weeks) | Core Switch Configuration Forecast | Days Passed Since Core Switch Configuration | Backhaul Delivery coordination (Est. 3 months) | Backhaul Delivery Forecast | Days Passed Since Backhaul Delivery | Integration (Est. 2 weeks) | Integration Completion Forecast | Days Passed Since Integration Completion | Construction Completion | Construction Completion Forecast | Days Passed Since Construction Completion | Optional: Customer Success Team to assist on training efforts to onboard new users (Vault) | QC site review (Est. 7 days) | QC Site Review Forecast | Days Passed Since QC Site Review | Site Walk (Est. 2 weeks) | Site Walk Forecast | Days Passed Since Site Walk | FNE Closeout Package (Est. 2 weeks) | FNE Closeout Package Forecast | Days Passed Since FNE Closeout Package | Accepts Network (Est. 1 week) | Network Acceptance Forecast | Days Passed Since Network Acceptance | Project Completion | Project Completion Forecast | Days Since Project Completion
2023-03-12 |  | 2023-03-15 | 2023-03-21 | 3 |  | 2023-03-17 | 6 | 2023-03-24 | 2023-03-28 | 6 | 2023-04-01 | 2023-04-04 | 7 | Yes | [5 empty] | Aerwave | 2023-04-10 | 2023-04-11 | 1 | 2023-04-10 | 2023-04-19 | 2 | 2023-04-11 | 2023-04-19 | 15 | 2023-05-01 | 2023-05-02 | 1 | 2023-04-23 | 2023-04-25 | 5 | 2023-04-28 | 2023-04-25 | 2 | 2023-05-01 | 2023-05-02 | 15 | 2023-05-10 | 2023-05-10 | 8 | 2023-05-05 | 2023-05-10 | 11 | 2023-05-15 | 2023-05-10 | 5 | 2023-05-20 | 2023-05-15 | 4 | 2023-05-25 | 2023-05-26 | 6 | 2023-06-01 | 2023-06-05 | 7 | 2023-06-10 | 2023-06-12 | 4 | 2023-06-15 | 2023-06-20 | 4 | 2023-06-20 | 2023-06-26 | 7 | 2023-06-28 | 2023-06-29 | 13 | 2023-07-14 | 2023-07-12 | 11 | Yes | 2023-07-30 | 12 | 2023-08-15 | 2023-08-08 | 12 | 2023-08-30 | 2023-08-24 | 67 | 2023-11-30 | 2024-01-03 | 15 | 2023-12-20 | 2023-12-14 | 4 | 2023-12-25 | 2023-12-25 | 8 | 2024-01-03 | 2024-01-03 | 6 | 2024-01-10 | 2024-01-12 | 8 | 2024-01-20 | 2024-01-19 | 15 | 2024-02-10 | 2024-01-30 | 3 | 2024-02-14 | 2024-02-20 | 178 | 2024-09-01 | 2024-08-28 | 178 | 2024-10-20 | 2024-10-25 | 12 | 2024-11-05 | 2024-10-29 | 176 | 2024-11-15 | 2024-11-26 | 93 | 2025-03-10 | 2025-03-11 | 12 | 2025-03-25 | 2025-03-24 | 76 | 2025-07-08 | 2025-07-15 | 11 |  | 2025-07-22 | 2025-07-17 | 18 | 2025-08-14 | 2025-08-05 | 13 | 2025-09-01 | 2025-08-28 | 8 | 2025-09-10 | 2025-09-10 | 8 | 2025-09-20 | 2025-09-24 | -50
2020-01-01 |  |  | 2020-01-10 |  | No
2021-01-01 |  | 2021-01-06 | 2021-01-12 | 4 | Yes | 2021-01-11 | 5 | 2021-01-15 | 2021-01-20 | 4 | 2021-01-20 | 2021-01-26 | 4 | No | [5 empty] | SBA | [6 empty] | 2021-01-25 | 2021-01-29 | 18 | 2021-01-30 | 2021-02-15 | 13 | 2021-02-07 | 2021-02-08 | 2 | 2021-02-09 | 2021-02-08 | 7 | 2021-02-17 | 2021-02-15 | 13 | 2021-02-28 | 2021-02-26 | 5 | 2021-03-04 | 2021-02-26 | 2 | 2021-03-05 | 2021-02-26 | 1 | 2021-03-05 | 2021-03-03 | 4 | 2021-03-10 | 2021-03-12 | 3 | 2021-03-14 | 2021-03-19 | 3 | 2021-03-17 | 2021-03-23 | 3 | 2021-03-20 | 2021-03-26 | 9 | 2021-04-01 | 2021-03-30 | 3 | 2021-04-05 | 2021-04-12 | 9 | 2021-04-15 | 2021-04-19 | 4 | No | 2021-04-20 | 4 | 2021-04-25 | 2021-04-29 | 5 | 2021-05-01 | 2021-05-04 | 65 | 2021-08-01 | 2021-09-03 | 10 | 2021-08-15 | 2021-08-13 | 5 | 2021-08-21 | 2021-08-18 | 6 | 2021-08-30 | 2021-08-31 | 7 | 2021-09-07 | 2021-09-08 | 7 | 2021-09-15 | 2021-09-16 | 4 | 2021-09-20 | 2021-09-24 | 9 | 2021-09-30 | 2021-09-29 | 188 | 2022-05-01 | 2022-04-22 | 188 | 2022-06-20 | 2022-06-24 | 10 | 2022-07-01 | 2022-06-29 | 184 | 2022-07-15 | 2022-07-22 | 70 | 2022-10-01 | 2022-11-04 | 14 | 2022-10-20 | 2022-10-14 | 105 | 2023-03-15 | 2023-03-10 | 4 |  | 2023-03-20 | 2023-03-24 | 19 | 2023-04-13 | 2023-04-03 | 12 | 2023-04-28 | 2023-04-27 | 6 | 2023-05-05 | 2023-05-09 | 7 | 2023-05-15 | 2023-05-19 | 566
2020-03-01 |  | 2020-03-06 | 2020-03-10 | 6 | Yes | 2020-03-14 | 9 | 2020-03-26 | 2020-03-24 | 7 | 2020-04-05 | 2020-04-06 | 5 | Yes | [12 empty] | 2020-04-10 | 2020-04-14 | 16 | 2020-04-30 | 2020-05-01 | 2 | 2020-04-20 | 2020-04-24 | 9 | 2020-04-30 | 2020-04-24 | 2 | 2020-05-01 | 2020-05-01 | 11 | 2020-05-09 | 2020-05-12 | 5 | 2020-05-13 | 2020-05-12 | 3 | 2020-05-05 | 2020-05-12 | 9 | 2020-05-16 | 2020-05-15 | 2 | 2020-05-19 | 2020-05-22 | 10 | 2020-06-01 | 2020-05-28 | 1336 |  | 2020-06-10
Formulas:
Explore Opportunity Forecast = IF(ISBLANK(Table13[[#This Row],[BD creates opportunity in CRM ]]), "", WORKDAY(Table13[[#This Row],[BD creates opportunity in CRM ]], 7))
BD Submission to Design Distro Forecast = IF(ISBLANK(Table13[[#This Row],[Date of Prospect Interest]]), "", WORKDAY(Table13[[#This Row],[Date of Prospect Interest]], 7))
Tracker Update Forecast = IF(ISBLANK(Table13[[#This Row],[BD submits email to NSE Design Distro]]), "", WORKDAY(Table13[[#This Row],[BD submits email to NSE Design Distro]], 7))
PM Check-in Forecast = IF(Table13[[#This Row],[SBA or Aerwave]] = "Aerwave", WORKDAY(Table13[[#This Row],[Program Manager adds request to tracker ]], 7), " ")
PM Submission to Aerwave Forecast = IF(Table13[[#This Row],[SBA or Aerwave]] = "Aerwave", WORKDAY(Table13[[#This Row],[P.M Check with BD OK to submit Aerwave]], 7), " ")
Sales Ops Peer Review Forecast = IF(ISBLANK(Table13[[#This Row],[Fin Analyst creates fin. model ]]), "", WORKDAY(Table13[[#This Row],[Fin Analyst creates fin. model ]], 7))
Finance Peer Review Forecast = IF(ISBLANK(Table13[[#This Row],[Fin Analyst creates fin. model ]]), "", WORKDAY(Table13[[#This Row],[Fin Analyst creates fin. model ]], 7))
Tax Financial Model Review Forecast = IF(ISBLANK(Table13[[#This Row],[Fin Analyst creates fin. model ]]), "", WORKDAY(Table13[[#This Row],[Fin Analyst creates fin. model ]], 7))
BD Review Forecast = IF(ISBLANK(Table13[[#This Row],[Program Manager Submits Fin. Model to BD for Review (Est. 2 days) ]]), "", WORKDAY(Table13[[#This Row],[Program Manager Submits Fin. Model to BD for Review (Est. 2 days) ]], 5))
BD Responds to Move Forward Forecast = IF(ISBLANK(Table13[[#This Row],[BD reviews Fin. Model Pricing ]]), "", WORKDAY(Table13[[#This Row],[BD reviews Fin. Model Pricing ]], 7))
Program Manager Validation Forecast = IF(ISBLANK(Table13[[#This Row],[BD Responds OK to Move Forward]]), "", WORKDAY(Table13[[#This Row],[BD Responds OK to Move Forward]], 7))
Full Proposal Forecast = IF(ISBLANK(Table13[[#This Row],[Program Manager creates 1 pager proposal (Est. 2 days) ]]), "", WORKDAY(Table13[[#This Row],[Program Manager creates 1 pager proposal (Est. 2 days) ]], 7))
BD Submits Proposal Forecast = IF(ISBLANK(Table13[[#This Row],[Program Manager creates full proposal (Est. 10 days) ]]), "", WORKDAY(Table13[[#This Row],[Program Manager creates full proposal (Est. 10 days) ]], 7))
M. Director Presents to CAC Forecast = IF(ISBLANK(Table13[[#This Row],[BD submits proposal ]]), "", WORKDAY(Table13[[#This Row],[BD submits proposal ]], 10))
CRM Update Forecast = IF(ISBLANK(Table13[[#This Row],[Proposal Acceptance Date ]]), "", WORKDAY(Table13[[#This Row],[Proposal Acceptance Date ]], 7))
Liason/Review Redlines Forecast = IF(ISBLANK(Table13[[#This Row],[Update record in CRM ]]), "", WORKDAY(Table13[[#This Row],[Update record in CRM ]], 7))
Draft Agreement Forecast = IF(ISBLANK(Table13[[#This Row],[Liaison/review redlines ]]), "", WORKDAY(Table13[[#This Row],[Liaison/review redlines ]], 90))
Agreement Execution Forecast = IF(ISBLANK(Table13[[#This Row],[Draft Agreement (Est. 90 days) ]]), "", WORKDAY(Table13[[#This Row],[Draft Agreement (Est. 90 days) ]], 10))
Kickoff Meeting Forecast = IF(ISBLANK(Table13[[#This Row],[Executed Agreement (10 days)]]), "", WORKDAY(Table13[[#This Row],[Executed Agreement (10 days)]], 3))
Budget Approval Forecast = IF(ISBLANK(Table13[[#This Row],[Prog Manager schedules Kick-off meeting (Est. 3 days) ]]), "", WORKDAY(Table13[[#This Row],[Prog Manager schedules Kick-off meeting (Est. 3 days) ]], 7))
Backhaul Order Forecast = IF(ISBLANK(Table13[[#This Row],[Budget Approvals (Est. 7 days) ]]), "", WORKDAY(Table13[[#This Row],[Budget Approvals (Est. 7 days) ]], 7))
Quote Update Forecast = IF(ISBLANK(Table13[[#This Row],[Order backhaul (Est. 7 days) ]]), "", WORKDAY(Table13[[#This Row],[Order backhaul (Est. 7 days) ]], 7))
Final BOM Forecast = IF(ISBLANK(Table13[[#This Row],[Quotes updates if changes in BOM list (Est. 7 days) ]]), "", WORKDAY(Table13[[#This Row],[Quotes updates if changes in BOM list (Est. 7 days) ]], 7))
PO Submission Forecast = IF(ISBLANK(Table13[[#This Row],[Final BOM (Est. 7 days) ]]), "", WORKDAY(Table13[[#This Row],[Final BOM (Est. 7 days) ]], 7))
RTP Forecast = IF(ISBLANK(Table13[[#This Row],[Executed Agreement (10 days)]]), "", WORKDAY(Table13[[#This Row],[Executed Agreement (10 days)]], 180))
Construction Start Forecast = IF(ISBLANK(Table13[[#This Row],[Coordinate materials logistics (Est. 8 weeks) ]]), "", WORKDAY(Table13[[#This Row],[Coordinate materials logistics (Est. 8 weeks) ]], 7))
Core Switch Configuration Forecast = IF(ISBLANK(Table13[[#This Row],[Monitor Construction Start (Est. 6 months) ]]), "", WORKDAY(Table13[[#This Row],[Monitor Construction Start (Est. 6 months) ]], 15))
Backhaul Delivery Forecast = IF(ISBLANK(Table13[[#This Row],[Monitor Construction Start (Est. 6 months) ]]), "", WORKDAY(Table13[[#This Row],[Monitor Construction Start (Est. 6 months) ]], 90))
Integration Completion Forecast = IF(ISBLANK(Table13[[#This Row],[Backhaul Delivery coordination (Est. 3 months) ]]), "", WORKDAY(Table13[[#This Row],[Backhaul Delivery coordination (Est. 3 months) ]], 10))
Construction Completion Forecast = IF(ISBLANK(Table13[[#This Row],[Monitor Construction Start (Est. 6 months) ]]), "", WORKDAY(Table13[[#This Row],[Monitor Construction Start (Est. 6 months) ]], 180))
QC Site Review Forecast = IF(ISBLANK(Table13[[#This Row],[Construction Completion]]), "", WORKDAY(Table13[[#This Row],[Construction Completion]], 7))
Site Walk Forecast = IF(ISBLANK(Table13[[#This Row],[QC site review (Est. 7 days) ]]), "", WORKDAY(Table13[[#This Row],[QC site review (Est. 7 days) ]], 10))
FNE Closeout Package Forecast = IF(ISBLANK(Table13[[#This Row],[Site Walk (Est. 2 weeks) ]]), "", WORKDAY(Table13[[#This Row],[Site Walk (Est. 2 weeks) ]], 10))
Network Acceptance Forecast = IF(ISBLANK(Table13[[#This Row],[FNE Closeout Package (Est. 2 weeks) ]]), "", WORKDAY(Table13[[#This Row],[FNE Closeout Package (Est. 2 weeks) ]], 7))
Project Completion Forecast = IF(ISBLANK(Table13[[#This Row],[Accepts Network (Est. 1 week) ]]), "", WORKDAY(Table13[[#This Row],[Accepts Network (Est. 1 week) ]], 10))
Days Since Project Completion = IF(ISBLANK(Table13[[#This Row],[Project Completion]]), " ", NETWORKDAYS(Table13[[#This Row],[Project Completion]], TODAY()))

## PreSales Prototype
PRESALES
Source | Status | CRM | CRM | CRM | CRM | CRM | CRM | CRM | Email | Ricardy | Ricardy | Ricardy | Ricardy | Ricardy | Ricardy | Ricardy | Ricardy | Ricardy | Ricardy | Ricardy | BD | BD | BD | BD | Design | [6 empty] | BD
Column1 | Design Stage | Opp Name | Opp ID | Deal Type | Property Type | Deal Stage | BD Name | #Units | Receive date | Kickoff date | ROM Request | ROM Receive | Backhaul Cost Request | Backhaul Cost Receive | OSP Request | OSP Receive | FM Request | FM receive | FM review | FM Approval meeting | 1-pager Submission to BD | Proposal Accepted | Firm Pricing request | Site walk & Firm quote | Final Design & BOM(20 calendar days from site walk) | FM request2 | FM Review3 | Tax Review | Tax Approval | Final proposal submission | CAC Presentation (If applicable) | BD submits proposal | Final Proposal Accepted | Legal agreement | Executed Agreement
| Completed | Carson Estates |  | Connected Venues |  |  | Christina | 262 | 2025-04-18 | 2025-05-13 | 2025-05-15 | 2025-06-04 | 2025-05-13 | 2025-05-30 | [6 empty] | 2025-06-05 | [7 empty] | 2025-01-01 | 2025-01-05 | 2025-01-06 |  | 2025-03-01 | 2025-07-04
| Completed | UT_Valley of Wildflower (Lennar development) |  | Connected Communities |  |  | Ramith | 1 | 2025-04-26 | 2025-05-06 | 2025-05-13 | 2025-05-29 | 2025-05-18 | 2025-06-04 | 2025-01-01 | 2025-01-04 |  |  |  |  | 2025-05-27
| Completed | AL_The Hub at Grants Hill |  | Connected Venues |  |  | Steven | 350 | 2025-04-30 | 2025-05-07 | 2025-05-19 | 2025-06-03 | 2025-05-30 | 2025-06-18 | 2025-02-01 | 2025-03-01 |  |  |  |  | 2025-05-24
Done | Completed | FL_Green District |  | Connected Venues/Wifi |  |  | Ramith | 6955 | 2025-05-03 | 2025-05-13 | 2025-03-18 | 2025-04-02 | 2025-05-15 | 2025-04-24 |  | 2025-04-24 |  |  |  |  | 2025-06-01
Hold | On Hold | Canvas at Wildwood |  | Connected Communities |  |  | Tyrone | 264 | 2025-05-04 | 2025-05-19 | 2025-03-18 | 2025-04-21 | 2025-05-30 | 2025-06-21 | 2025-03-18 | 2025-05-02 |  |  |  |  | 2025-05-30
Lost | Completed | The Estates at Hurstmont |  | Connected Venues |  |  | Tyrone | 210 | 2025-05-08 | 2025-05-20 | 2025-04-14 | 2025-05-02 | 2025-04-14 | 2025-05-13 | 2025-04-14 | 2025-05-16 |  | 2025-05-15 |  |  | 2025-05-28
FM | Completed | Alyster |  | Connected Communities |  |  | Christina | 102 | 2025-05-09 | 2025-05-24 | 2025-05-06 | 2025-05-21 | 2025-05-06 | 2025-05-19 | 2025-01-20 | 2025-05-21 |  | 2025-05-22 |  |  | 2025-06-02
Hold | On Hold | eleva |  | Connected Communities |  |  | Christina | 151 | 2025-05-10 | 2025-05-22 | 2025-01-22 | 2025-05-21 | 2025-05-30 | 2025-06-19 | 2025-01-22 | [5 empty] | 2025-05-24
Hold | On Hold | Mondu |  | DAS |  |  | Ramith | 1 | 2025-05-12 | 2025-06-01 | 2025-04-11 | 2025-04-28 | 2025-04-11 | 2025-05-02 | 2025-04-11 | [5 empty] | 2025-06-05
Network Takeover | In Design | Omni Nashville |  | DAS |  |  | Adam | N/A | 2025-05-14 | 2025-05-24 | 2025-04-24 | 2025-05-10 | 2025-05-12 | 2025-06-01 | 2025-04-24 | [5 empty] | 2025-06-04
Hold | FM Request | Northern Nevada Sierra |  | DAS |  |  | Adam | N/A - 1 Bulding | 2025-05-16 | 2025-05-26 | 2025-04-29 | 2025-05-19 | 2025-05-23 | 2025-06-15 | 2025-04-29 | [5 empty] | 2025-06-15
[9 empty] | 2025-04-11 | 2025-04-22 | 2025-04-11 | 2025-04-30 | 2025-04-10 | 2025-05-01 | 2025-04-11 | 2025-04-25 | 2025-04-25 | 2025-05-05 |  |  | 2025-05-22 |  |  | 2025-05-25 | 2025-06-01 | 2025-02-01 | 2025-02-01 | 2025-02-01 | 2025-02-10 | 2025-02-13 | 2025-02-25 | 2025-03-01 | 2025-03-06 | 2025-06-20 | 2025-07-01
[9 empty] | 2025-04-10 | 2025-04-20 | 2025-04-12 | 2025-04-22 | 2025-04-12 | 2025-04-23 | 2025-04-12 | 2025-04-23 | 2025-04-24 | 2025-04-26 |  |  | 2025-05-05 |  |  | 2025-05-07 | 2025-05-15 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-11 | 2025-01-05 | 2025-04-01 | 2025-04-12
| Completed | FL_Pearl Street N11_WIFI |  | Connected Venues |  |  | Tyrone | 205 | 2025-04-12 | 2025-01-31 | 2025-02-15 | 2025-02-18 | 2025-02-20 | 2025-02-28 |  |  | 2024-04-26 | 2025-04-30 |  |  | 2025-02-10 |  |  | 2025-02-15 | 2025-03-01 | 2025-03-01 | 2025-03-03 | 2025-03-01 | 2025-03-13 | 2025-03-15 | 2025-03-30 | 2025-04-10 | 2025-04-01 | 2025-08-01 | 2025-08-15
| Completed | Toscana at Valley Ridge |  | Connected Venues |  |  | Christina | 288 | 2025-04-14 | 2025-04-23 | 2025-04-30 | 2025-05-07 | 2025-05-08 | 2025-05-28 |  |  | 2025-05-09 | 2025-05-09 |  |  | 2025-05-04 |  |  | 2025-05-05 | 2025-06-01 | 2025-05-01 | 2025-05-03 | [5 empty] | 2025-07-01 | 2025-09-29
| Completed | Clearview |  | Connected Venues |  |  | Christina | 376 | 2025-04-15 | 2025-04-29 | 2025-05-07 | 2025-05-10 | 2025-05-14 | 2025-05-30 | [6 empty] | 2025-05-19 |  |  | 2025-05-28 | 2025-06-28 | [7 empty] | 2025-08-01 | 2025-10-10
| Completed | Melrose |  | Connected Venues |  |  | Christina | 359 | 2025-04-19 | 2025-04-27 | 2025-05-09 | 2025-05-20 | 2025-05-02 | 2025-05-25 | [6 empty] | 2025-05-11
Hold | Completed | OR_Ferguson Rd Quarterra_Wi-Fi |  | Connected Venues |  |  | Ramith | 264 | 2025-04-20 | 2025-04-26 | 2025-05-20 | 2025-05-30 | 2025-05-27 | 2025-06-06 | [6 empty] | 2025-05-16
| Completed | FL Venice Shores Luxury Apartments WIFI |  | Connected Venues |  |  | Tyrone | 293 | 2025-04-22 | 2025-04-25 | 2025-04-30 | 2025-05-07 | 2025-05-09 | 2025-06-07 | [6 empty] | 2025-05-13
Lost | Completed | Waterman RFP |  | Master Communities |  |  | Tyrone | 351 | 2025-04-23 | 2025-04-28 | 2025-05-05 | 2025-05-08 | 2025-05-16 | 2025-06-02 | [6 empty] | 2025-05-09
Hold | Completed | Asante Temp Tower 2 |  | DAS |  |  | Ramith | 1 | 2025-04-25 | 2025-04-26 | 2025-05-14 | 2025-05-27 | 2025-05-17 | 2025-06-02 | [6 empty] | 2025-05-05
| Completed | IN_McCromicks Greek |  | Connected Venues |  |  | Ramith | 1 | 2025-04-27 | 2025-05-03 | 2025-05-10 | 2025-05-11 | 2025-05-17 | 2025-06-04 | [6 empty] | 2025-05-16
Done | Completed | FL_Waterlin |  | Connected Communities |  |  | Steven | 15000 | 2025-04-28 | 2025-05-06 | 2025-05-20 | 2025-05-30 | 2025-05-16 | 2025-06-03 | [6 empty] | 2025-05-23
Done | Completed | TX-Honey Creek |  | Connected Communities |  |  | Steven | 3041 | 2025-04-29 | 2025-05-07 | 2025-05-17 | 2025-05-30 | 2025-03-01 | 2025-04-08 | 2025-03-21 | 2025-03-24 |  |  |  |  | 2025-05-26
Lost | Completed | Waterman Village |  | Connected Venues |  |  | Tyrone | 350 | 2025-05-01 | 2025-05-09 | 2025-05-26 | 2025-06-05 | 2025-05-27 | 2025-06-16 | [6 empty] | 2025-05-29
| Completed | NY_State Street Apartment - Datavalet |  | Connected Venues |  |  | Tyrone | 371 | 2025-05-02 | 2025-05-06 | 2025-03-18 | 2025-03-24 | 2025-03-30 | 2025-04-20 | 2025-03-18 | [5 empty] | 2025-05-16
Hold | On Hold | 707 Terry Coffee Shop |  | Connected Venues |  |  | Christina | 1 | 2025-05-05 |  | 2025-04-01 | 2025-04-06 | 2025-04-19 | 2025-05-10
Done | On Hold | Glasgow |  | Connected Communities |  |  | Tyrone | 310 | 2025-05-06 | 2025-05-13 | 2025-04-08 | 2025-04-15 | 2025-04-08 | 2025-04-15 | 2025-04-08 | 2025-04-22 |  | 2025-04-22 |  |  | 2025-05-31
Lost | Completed | Airabella |  | Connected Communities |  |  | Tyrone | 500 | 2025-05-07 | 2025-05-15 | 2025-04-07 | 2025-04-15 | 2025-04-15 | 2025-04-16 | 2025-04-07 | 2025-05-16 |  | 2025-04-22 |  |  | 2025-05-22
Hold | On Hold | Big Brooke Temp Tower |  | DAS |  |  | Ramith | 1 | 2025-05-11 | 2025-05-27 | 2025-04-11 | 2025-04-22 | 2025-04-11 | 2025-05-04 | 2025-04-11 | [5 empty] | 2025-06-02
FM | FM Request | Bermuda Village |  | Connected Venues |  |  | Tyrone | 313 | 2025-05-13 | 2025-05-29 | 2025-04-28 | 2025-05-06 | 2025-04-28 | 2025-05-09 | 2025-04-28 | 2025-05-06 |  |  |  |  | 2025-06-11
Hold | Gathering Requirement | Golden Gem Resi |  | Connected Venues |  |  | Steven | 54 | 2025-05-17 | 2025-06-06 | 2025-04-22 | 2025-04-29 | 2025-05-01 | 2025-05-22 | 2025-04-22 | 2025-04-23 |  |  |  |  | 2025-06-25
Network Takeover | On Hold | Bosa REN |  | Connected Venues |  |  | Christina | 457 | 2025-05-18 | 2025-06-08 | 2025-04-01 | 2025-04-10 | 2025-05-04 | 2025-05-24 | 2025-04-01 | [5 empty] | 2025-06-25
OSP | In Design | Serenade |  | Connected Venues |  |  | Steven | 888 | 2025-05-19 | 2025-06-03 | N/A | N/A | N/A | N/A | 2025-05-21 | [5 empty] | 2025-06-20
OSP | In Design | The perle |  | Connected Venues |  |  | Tyrone | 230 | 2025-05-20 | 2025-06-10 | 2025-05-09 | 2025-05-22 | 2025-05-09 | 2025-05-13 | 2025-05-09 | [5 empty] | 2025-06-28
OSP | In Design | SBA Jax Data Center |  | Connected Venues |  |  | Ramith | 92 | 2025-05-21 | 2025-06-01 | 2025-05-23 | 2025-05-31 | N/A | N/A | [6 empty] | 2025-06-18
Design | In Design | The wellinton |  | Connected Venues |  |  | Steven |  | 2025-05-22 | 2025-06-12 | 2025-05-28 | 2025-05-30 | 2025-05-28 | 2025-06-17 | 2025-05-28 | [5 empty] | 2025-07-02
OSP | In Design | 37 Tree view |  | Connected Venues |  |  | Tyrone | 300 | 2025-05-23 | 2025-06-08 | 2025-05-29 | 2025-06-02 | 2025-05-29 | 2025-06-20 | 2025-05-29 | [5 empty] | 2025-06-09
Network Takeover | In Design | Prisma Health ¦ Blount Memorial Hospital |  | DAS |  |  | Adam | 6 Floors | 2025-05-24 | 2025-06-04 | N/A | [9 empty] | 2025-06-20
| Gathering Requirement | Veridea |  | Connected Communities |  |  | Steven |  | 2025-05-25 | 2025-06-15 | 2025-06-18 | 2025-06-29 | 2025-07-01 | 2025-07-10 | [6 empty] | 2025-07-01
| Completed | West Jefferson Medical Center Enterprise DAS |  | DAS |  |  | Benson | 419 | 2025-04-13 | 2025-04-23 | 2025-04-29 | 2025-05-04 | 2025-05-03 | 2025-05-30 |  |  | 2025-05-01 | 2025-05-02 |  |  | 2025-05-23 |  |  | 2025-05-26 | 2025-06-20 | 2024-04-01 | 2025-04-03 | 2025-04-01 | 2025-04-09 | 2025-04-10 | 2025-04-30 | 2025-05-09 | 2025-05-10 | 2025-10-01 | 2025-10-14
| Completed | Enclave on Golden Triangle |  | Connected Venues |  |  | Christina | 273 | 2025-04-16 | 2025-04-27 | 2025-05-08 | 2025-05-14 | 2025-05-13 | 2025-06-01 | [6 empty] | 2025-05-27 |  |  | 2025-07-01 | 2025-07-02 | 2025-08-01 | 2025-08-02 | [5 empty] | 2025-04-01 | 2025-07-20
| Completed | Walmart Enterprise DAS |  | DAS |  |  | Steven | N/A | 2025-04-21 | 2025-04-29 | 2025-05-11 | 2025-05-24 | 2025-05-18 | 2025-05-31 | [6 empty] | 2025-05-29
Hold | Completed | Romano Capital - WA_Palisade_NC |  | Connected Communities |  |  | Barrett/Christina | 450 | 2025-04-24 | 2025-05-02 | 2025-05-10 | 2025-05-22 | 2025-04-01 | 2025-04-17 | [6 empty] | 2025-06-02
| Completed | Heights at Meridian |  | Connected Venues |  |  | Christina | 339 | 2025-04-17 | 2025-05-04 | 2025-05-10 | 2025-05-21 | 2025-05-16 | 2025-06-03 | [6 empty] | 2025-05-30 | [11 empty] | 2025-02-03 | 2025-06-13
Done | Completed | RS Apartments_Retrofit_GPON |  | Connected Venues |  |  | Ramith | 306 | 2025-05-15 | 2025-05-27 | 2025-04-29 | 2025-05-05 | 2025-04-29 | 2025-05-19 | 2025-04-29 | 2025-05-14 |  | 2025-05-23 |  |  | 2025-06-23
Total | [8 empty] | 46 |  |  | 44 |  | 43 |  | 14 |  | 10 | [6 empty] | 7 |  | 6 |  | 5 | 5 | 5 | 4 |  | 9 | 4
Formulas:
Ricardy = [Ricardy]+20
Ricardy = [Email]+10
BD = [Ricardy]+23
Legal agreement = [Final Proposal Accepted]+125

## Construction Prototype
CONSTRUCTION
Construction Stage | Site Name | Site ID | A&E Request | A&E receive | Budget Request | Budget Approval | Quotes from OEM | PO Request for OEM | PO Approval | backhaul ordered | RTP Request | RTP Approved | RFP Request | RFP Received | PO for GC Request | PO for GC Approved | Construction Start | Construction Complete | Build (6 months) | Integration Start | Integration Complete | Close Out Package(2weeks from integration complete) | Acceptance testing (2 weeks from close out package) | Customer acceptance(1 month after acceptance testing) | Operations handoff(1 week after customer acceptance) | FNE Date | FNE Notice | PMDB Update | Revenue Billing(PMDB)
C. Design | Chacra Canyon | [6 empty] | 2025-01-01 | 2025-03-01 | [16 empty] | DAS Site Mod - No FNE
C. Design | Emory Musculoskeletal Institute (EP MSK) | [14 empty] | 2025-05-30
C. Design | Emory University Hospital Midtown |  | 2025-02-18 | [7 empty] | 2025-03-20 |  |  | 2025-03-28 |  | 2025-05-30
C. Design | Glenwood Canyon ATT Additional Node | [24 empty] | No FNE since this is just a Site Mod.
C. Design | Glenwood Canyon Backup Power | [24 empty] | No FNE since this is just a Site Mod.
C. In progress | Laurens MRI | [24 empty] | DAS Site Mod - No FNE
C. In progress | Minnesota State Fairgrounds | [15 empty] | 2023-09-25 | 2024-03-13 |  | 2024-03-13 | 2024-03-13 |  |  |  |  | DAS Radio Swap - No FNE
C. Design | Mt. Sinai | [9 empty] | 2025-05-27 |  | 2025-05-27 | 2025-06-11 | [11 empty] | Need to Forecast Once GC is Awarded
C. Design | Omni Hilton Head | [24 empty] | No FNE since this is in the Sales/Business Development Phase.
C. In progress | Packing District: High Point Climbing | [24 empty] | No FNE since this is just additional customer/client adds
C. Design | Palisades South (Debeque)
[5 empty] | 2025-05-01 | 2025-05-07 |  | 2025-02-01 | 2025-02-06 | [5 empty] | 2025-01-05 | 2025-01-09 |  |  |  | 2025-02-03 | 2025-02-21 | 2025-03-11 | 2025-03-29 | 2025-04-28 | 2025-05-07 | 2025-02-05 | 2025-02-06 | 2025-02-08 | 2025-02-15
|  |  | 2025-01-03 | 2025-01-16 | 2025-04-23 | 2025-04-28 |  | 2025-01-03 | 2025-01-07 | [5 empty] | 2025-01-01 | 2025-01-30 |  |  |  | 2025-01-04 | 2025-02-01 | 2025-02-21 | 2025-02-28 | 2025-04-09 | 2025-04-29 | 2025-01-05 | 2025-01-08 | 2025-01-11 | 2025-01-12
C. In progress | Alan B Miller |  | 2025-04-24 |  | 2025-06-01 | 2025-06-04 |  | 2025-03-01 | 2025-03-08 |  | 2024-10-11 | 2025-05-07 | 2025-04-01 | 2024-04-15 | 2025-05-20 | 2025-05-21 |  |  |  | 2025-03-01 | 2025-03-31 | 2025-04-21 | 2025-04-26 | 2025-06-15 | 2025-06-24 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-12
| Asante-1 | [11 empty] | 2025-03-01 | 2025-03-20 | [11 empty] | On Hold - No FNE for Now
FNE | Baptist Parkridge | [9 empty] | 2024-04-01 | 2024-10-10 | 2025-05-01 | 2025-05-20 | [11 empty] | DAS Carrier Add - No FNE
C. Design | Debeque Canyon | [24 empty] | DAS Site Mod - No FNE
C. Design | Debeque Canyon | [24 empty] | DAS Site Mod - No FNE
C. Design | Emory Decatur Hospital |  | 2024-10-09 | 2025-01-13 | [6 empty] | 2025-03-20 | 2025-07-23 |  | 2025-03-28 |  | 2025-05-30
C. Design | Emory Health Sciences Research |  | 2024-11-13 | 2025-04-02 | [6 empty] | 2025-03-20 | 2025-07-23 |  | 2025-03-28 |  | 2025-05-30
C. Design | Emory Long Term Acute Care |  | 2024-11-14 | 2025-04-01 | [6 empty] | 2025-03-20 |  |  | 2025-03-28
C. Design | Emory Orthopaedics Hospital |  | 2024-11-14 | 2025-04-24 | [6 empty] | 2025-03-20 |  |  | 2025-03-28
C. Design | Emory Saint Joseph's Hospital
C. Design | Emory University Hospital (Plus A, B, C Clinic - ATT EOL)
C. Design | Emory Wesley Woods Geriatric Hospital |  | 2024-11-06 | 2025-04-01 | [6 empty] | 2025-03-20 |  |  | 2025-03-28 |  | 2025-05-30
C. Design | FIU
C. Design | Glenwood Canyon Backup Power
C. Design | Glenwood Canyon Backup Power
C. Design | Hyatt Regency Orlando
C. Design | Omni Championsgate Design
C. Design | Packing District: 4Roots | [24 empty] | Need to Forecast Once GC is Awarded
C. Design | Parcel B DAS | [24 empty] | FNE won't be determined until all agreements and contracts are executed
C. Design | Parshall
FNE | PH Greer Memorial Hospital |  | 2024-03-14 | 2024-06-14 |  |  |  | 2024-10-18 | 2025-01-06 |  | 2024-05-01 | 2024-11-01 |  |  |  | 2024-06-10 | 2024-11-11 | 2025-03-26 |  | 2025-03-26 | 2025-03-26 |  |  |  |  | 2025-03-26
C. Design | PH Midlands NE MACC | [9 empty] | 2025-05-27 |  | 2025-05-27 | 2025-06-11 | [11 empty] | Need to Forecast Once GC is Awarded
C. In progress | Prisma Greenville Memorial Hospital | [9 empty] | 2022-02-01 | 2022-08-12 | [13 empty] | No FNE since this just a maintenance request.
C. In progress | Rancho Springs |  | 2022-03-01 | 2023-03-07 |  |  |  | 2023-04-04 | 2023-05-09 |  | 2024-09-01 | 2024-02-27 |  |  |  | 2024-09-13 | 2023-10-12
C. In progress | Richland Hospital |  | 2024-09-18 | 2025-01-13 |  |  |  | 2024-09-27 | 2024-12-05 |  | 2024-09-01 | 2025-02-17 |  |  |  | 2024-10-01 | 2024-09-09
C. Design | St. Charles Convention Center and Hotel
C. In progress | State of Michigan Capitol Campus | [9 empty] | 2020-12-01 | [5 empty] | 2021-08-02 | 2022-06-22 |  | 2022-06-22 | 2022-06-22 |  |  |  |  | DAS Radio Swap - No FNE
| Asante Temp Tower #2 | [11 empty] | 2025-01-03 | 2025-02-01 | [5 empty] | 2025-04-02 | 2025-05-02 | 2025-05-21 | 2025-06-20 | 2025-07-31 | 2025-08-03 | On Hold - No FNE for Now
C. Design | Belle Isle Phase 2 | [9 empty] | 2021-07-01 | 2022-08-25 | [13 empty] | Need to Forecast Once GC is Awarded
C. In progress | Dr Phillips Center | [9 empty] | 2021-10-01 | 2023-12-07 | [13 empty] | DAS Carrier Add - No FNE
C. Design | Emory Hillandale Hospital |  | 2024-11-15 | [7 empty] | 2025-03-20 |  |  | 2025-03-28 |  | 2025-05-30
FNE | Cedar Hill Medical |  | 2024-09-09 | 2025-01-13 |  |  | 2024-11-01 | 2024-11-01 | 2024-11-01 |  | 2024-10-11 | 2025-01-08 |  |  |  | 2025-01-06 | 2025-01-13 | 2025-03-28 |  | 2025-03-28 | 2025-03-28 |  |  |  |  | 2025-04-25
C. In progress | Packing District: Momentic Studios ORPD LLC | [24 empty] | Need to Forecast Once GC is Awarded
C. Design | The Cliffs at Walnut Cove |  | 2025-02-24 | 2025-03-01 | [6 empty] | 2025-01-02
| Valley of Wildflower (Temp Tower #3) | [24 empty] | On Hold - No FNE for Now
C. In progress | West Henderson |  | 2024-10-22 | 2024-12-27 |  |  |  | 2024-10-15 | 2024-11-12 |  | 2024-09-01 | 2024-12-12 |  |  |  | 2024-10-21 | 2024-11-04 | 2024-12-13 |  | 2024-12-13 | 2024-12-13 |  |  |  |  | DAS Site Mod - No FNE
C. In progress | Westgate Mall |  | 2024-01-17 | 2024-04-12 |  |  |  | 2024-05-29 | 2024-07-02 |  | 2025-03-14 | 2025-01-15 |  |  |  | 2024-09-03 | 2025-01-28 | 2025-04-22 |  | 2025-04-22 | 2025-04-22
Total |  |  |  | 13 |  | 3 |  |  | 10 |  |  | 13 |  | 13 |  | 15 | 8 |  |  |  | 10 | 4 | 4 | 4 | 4 |  | 3 | 3 | 3
Formulas:
Integration Complete = [Integration Start]+18
FNE Notice = [FNE Date]+1
PMDB Update = [FNE Notice]+2
Revenue Billing(PMDB) = [FNE Notice]+9
RFP Received = [RFP Request]+19
RTP Approved = [RTP Request]+125

## Old
|  |  | Weekly Report | [5 empty] | Design | [5 empty] | Planning / Procurement | [5 empty] | RTP | [9 empty] | Circuit |  |  | Construction | [5 empty] | Integration |  |  |  |  | COP |  |  | FNE | [6 empty] | Budget
Projects | Construction | SBA CM | Progress Report | Impediments | Support Needs | Next Steps | Landlord | Executed Agreement | Solution | DATE of A&E Site Walk | DATE CDs received | Design REV | DATE BoM Received | DATE of Desgin to CX Handoff | RFP Received | DATE Of GC Award | OEM | GC | Materials Vendor(s) | DATE(s) of Ordered Materials | RTP Submission | Title | Zoning | Lease | Licensing | Permits | Asbestos Testing | NPA Review | NEPA Review | RTP Approval | Circuit Provider | (F) Circuit Install | (A) Circuit Install | Construction Kickoff Call | (F) Construction Start | % Construction Complete | (A) Construction Start | (F) Construction Complete | (A) Construction Complete | Monitoring Gear | (F) Integration Start | (A) Integration Start | (F) Integration Complete | (A) Integration Complete | COP & Checklist | DATE of Request to Customer | DATE of Customer Acceptance | Baseline FNE | (F) FNE | (A) FNE | FNE Quarter | CX to Ops Handoff | Site Admin / Billing Contact | Revenue Start | JMS BDGT Labor | JMS Actual Labor | JMS Remainig Labor | Labor 30% | 30% Payment | Labor 60% | 60% Payment | Labor 90% | 90% Payment | Full Payment | JMS (F) Materials | JMS (A) Materials | (V) Materials
PH Greer Memorial Hospital | FNE Ready | Justin Shorey | (1) Followed up again w Adam RE ATT and TMO joining system. (2) Conducted additional call w VZW and Prisma to coordinate VZW commissioning, with a new forecast date for VZW commissioning for Approx. 5/16/2025. |  |  | (1) Complete final punch walk and COP (2) Get Verizon on the system. (3) resolve TMO and AT&T solution w Adam and team (4) Send final COP to Prisma once VZW is commissioned |  | Executed | Carrier DAS |  |  |  | Received | Complete |  |  |  | Mcomm |  | Fully Received | [9 empty] | RTP Approved |  |  |  |  | 2024-11-04 | 100% |  | 2025-04-04 |  | Received | Complete |  |  |  | Complete |  | Accepted |  | 2025-03-26 |  | Q1 | Complete |  |  | 130886.1 | 86639.22 | 44246.88 | 39265.83 |  | 78531.66 |  | 117797.49 |  |  | 145194 | 150913.67 | -5719.67
Cedar Hill Medical | FNE Ready | Sean Ramjas | FNE |  |  |  | UHS | Executed | Enterprise DAS |  |  | REV 4 | Received | Complete |  |  |  | Widelity & TTS |  | Fully Received | [9 empty] | RTP Approved |  |  |  |  | 2025-01-13 | 100% |  | 2025-04-18 |  | Received | Complete |  |  |  | Complete |  | Requested |  | 2025-04-25 |  | Q2 | Started |  | 2025-04-01 | 210000 | 100500 | 109500 | 63000 |  | 126000 |  | 189000 |  |  | 148162 | 114444.61 | 33717.39
Westgate Mall | FNE Ready | Sean Ramjas | (1) DAS installation complete (antenna system) |  |  | (1) final site walk for next Tuesday. (2) Send COP to AT&T |  | Executed | Carrier DAS |  |  |  | Received | Complete |  |  |  | TTS |  | Fully Received | [9 empty] | RTP Approved |  |  |  |  | 2025-01-28 | 99% |  | 2025-04-30 |  | N/A | Pending |  |  |  | Not Started |  | Not Requested |  | 2025-04-30 |  | Q2 | Not Complete |  |  | 143107.75 | 97220.16 | 45887.59 | 42932.33 |  | 85864.65 |  | 128796.98 |  |  | 55620 | 54666.61 | 953.39
Rancho Springs | At Risk | Sean Ramjas | (1) Site walk completed with WP for SOW to complete eletrical install. (2) Quote received and PO issued to WP. | (1) GC True Access has not been paying their sub contractors (2) Legal issues |  | (1) Working with Carlos on budget increase for monies owe to sub-contractors from TruAccess |  | Executed | Carrier DAS |  |  |  | Received | Complete |  |  |  | True Access |  | Fully Received | [9 empty] | RTP Approved |  |  |  |  | 2024-10-16 | 95% |  | 2025-05-30 |  |  | Pending |  |  |  | Not Started |  | Not Requested |  | 2025-05-30 |  | Q2 | Not Complete |  |  | 328037.72 | 323041.91 | 4995.81 | 98411.32 |  | 196822.63 |  | 295233.95 |  |  | 109264.74 | 106264.54 | 3000.2
Alan B Miller | Not Awarded | Sean Ramjas | (1) Executed contract. Installation to start in June 2025. (2) Hosted call to review CDs with UHS and Turner (3) Issued RFP for CX GC |  |  | (1) Need BOM from Daniel (2) Request quotes for passive (Accutech/Alliance) and active gear (ADRF) (3) Award GC |  | Executed | Enterprise DAS |  | Completed by Smart RF. Dewberry to complete commerical for public das | REV 7.1 4/28/2025 | Completed | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Not Selected |  |  |  | 2025-06-02 | 0% |  | 2025-10-31 |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Started |  | 2025-10-31 |  | Q4 | Not Started |  | 2025-09-01 | 246200 | 6000 | 240200 | 73860 |  | 147720 |  | 221580 |  |  | 311710 | $- | 311710
Cliffs Walnut Cove | Awarded | Justin Shorey | (1) Initiated review call with design team (2) Coordinating w Lael, Jack, and Craig @ VZW to get them to join. (3) Scheduled trileaf for NEPA. | (1) Project schedule: Waiting on carriers. (2) Waiting on NEPA (100 days) (3) Verizon does not want to pay to join the system. | NEPA | (1) Need to double check complete BOM/design against vendor quotes to confirm all passive materials accounted for. (2) Need to review and approve updated drawing/design (3) Conduct a drawing/design review call w The Cliffs for approval/fine tuning for aesthetics once we get the drawings to that point with Dewberry. (4) Follow up with RTP for approvals. (5) Track shipment of Cisco Meraki MX. (6) Electrical SOW. (6) Coordinate trileaf site walk. |  | Executed | Enterprise DAS |  | Needs CDs from Dewberry. | 4/29/25 Waiting on ADRF pricing. Needs circuit analysis. | Justin to coordinate CDs with Dewberry and follow up with design. | Not Started |  |  |  | Verita |  | Partially Ordered | [9 empty] | In-Progress | Not Selected |  |  |  | 2025-07-07 | 0% |  | 2025-09-18 |  | Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | 2025-11-28 |  | Q4 | Not Started |  | 2025-06-01 | 91078 | $- | 91078 | 27323.4 |  | 54646.8 |  | 81970.2 |  |  | 60126 | $- | 60126
Baptist Parkridge | FNE Ready: Upgrade | Justin Shorey | (1) Setup AT&T integration and commissioning for Monday. (2) Conducted site walk w VZW and Prisma for transport installation. (3) Schedule Mcomm to complete GPS antenna re-mounted next week. Set up site schedule for next week to change GPS connector. (4) Coordinated w Ricky at GTS to get them in for cATT commissioning. (5) Requested PO for M Comm for ATT commissioning. |  |  | (1) Follow up with carriers (AT&T) and internal team for BTS installation, integration, and turn up dates. VZW shoud be end of May. ATT possibly need GTS on site. (2) Ensure that Mcomm repairs GPS. |  |  | Upgrade |  |  |  | N/A | [16 empty] | N/A | Lumen | Complete |  |  |  | 10% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
AZ18C66-P Asante 1 | FNE Ready: Upgrade | Sean Ramjas | (1) FNE complete and announced 3/3/25 (2) Received quotes from EWS for labor on tower mod (height increase) | Needs more information from the developer. ON HOLD. 4.25.25 |  | (1) Waiting on final design from RF (2) Obtain quotes from vendors |  |  | Upgrade |  |  |  | N/A | [6 empty] | Fully Received | [9 empty] | RTP Approved |  |  |  |  | N/A | 0% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A | 36260.24 | 36130 | 130.24 | 10878.07 |  | 21756.14 |  | 32634.22 |  |  | 60546.25 | 60331.51 | 214.74
FL91000-D Dr Phillips Center | FNE Ready: Upgrade | Sean Ramjas | (1) Completed site walk with Verizon (2) Completed site walk with Dewberry and Electrical vendor (3) Sent pricing to Benson for Verizon. |  |  | (1) Execute agreement between SBA and Verizon. (2) Waiting on quote for Electrical vendor (3) CDs from Dewberry (4) Provide Sales the construction cost to add VZW |  |  | Upgrade |  |  |  | N/A | [16 empty] | N/A |  |  |  |  | N/A | 10% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
GMH- Troubleshooting/Innowave Rip and Replace | FNE Ready: Upgrade | Justin Shorey | (1) Cofirmed SOW with internal team (2) followed up for funding (3) responded to customer compliant in CTC (4) performed site walk with Prisma. | Funding | Need aproval for funding | (1) Obtain budget approval (2) Work with Sheriffa to Issue RSMPO for labor and materials |  |  | Upgrade |  |  |  | N/A | [16 empty] | N/A |  |  |  |  | N/A | 0% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
MI50309-D State of Michigan Capitol Campus | FNE Ready: Upgrade | Sean Ramjas | (1) Site modification: AT&T to swap Nokia for Ericcson gear. (2) Provided quote to sales for C&I support. |  |  | (1) Benson working with AT&T for agreement. |  |  | Upgrade |  |  |  | N/A | [6 empty] | N/A | [9 empty] | N/A | Comcast |  |  |  | N/A | 10% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
MN49504-D Minnesota State Fairgrounds | FNE Ready: Upgrade | Sean Ramjas | (1) Site modification: AT&T to swap Nokia for Erickson gear. (2) Received quote from MP and forwarded to Benson |  |  | (1) Benson working with AT&T for agreement. |  |  | Upgrade |  |  |  | N/A | [6 empty] | N/A | [9 empty] | N/A | Comcast |  |  |  | N/A | 10% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
Packing District: High Point Climbing | FNE Ready: Upgrade | Sean Ramjas | (1) Confirmed FNE (2) John sent legal notice of substaintial completion |  |  | (1) Need to follow up with Elyinn and team for relocation of monitoring gear to the exterior. |  |  | Upgrade |  |  |  | N/A | [6 empty] | Fully Received | [9 empty] | N/A |  |  |  |  | N/A | 100% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
Parcel B | FNE Ready: Upgrade | Justin Shorey | (1) Obtained key from Cogency and returned to site (2) Followed up with design team for adjustments (3) Conducted site survey for DAS and created and submitted site photo package for design team. |  | (1) Need RF design proposal from RF team. Marlon is working on this request. (2) Cogency to locate and send back IDF cabinet keys. | (1) Work with design and sales for design proposal for basement/parking garage. (2) return key to site. |  |  | Upgrade |  |  |  | N/A | [6 empty] | Fully Received | [9 empty] | N/A | Lumen |  |  |  |  | 100% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
SC1B0CE-D PH Midlands NE MACC | Not Awarded | Sean Ramjas | (1) Customer sent PO in March 2025 | (1) JMS budget needs labor and materials |  | (1) Send construction SOW to sub contractors for RFQ (2) Review design (3) Issue RFP (4) Obtain quotes for materials |  | Pending | Enterprise DAS |  |  |  | Not Started | Not Started | [5 empty] | Not Ordered | [9 empty] | Not Started | Not Selected |  |  |  | Pending | N/A |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  |  | Not Started |  | Pending | $- |  | $- | $- |  | $- |  | $- |  |  | $- |  | $-
West Henderson | FNE Ready: Upgrade | Sean Ramjas | (1) Sent pricing to sales and Carlos H 4.25.25 | Signal issues. | SBA design to support signal enhancement | (1) Approve budget (2) Schedule construction |  |  | Upgrade | [10 empty] | N/A | [9 empty] | N/A |  |  |  |  | N/A | 10% |  | N/A | [10 empty] | N/A |  |  |  |  | N/A |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
AZ1B139-P Asante Temp Tower #2 | At Risk | Sean Ramjas | (1) Lennar approved deployment of this second tower. (2) Quote received from EWS for labor for installation of tower (4) Obtained from ARE for tower (materials) | ON HOLD 4.25.25 |  | (1) Finalize design and BoM (2) Finalize RTP process (3) Obtain updated quotes based on new design. |  | Executed |  |  |  |  | Not Started | Not Started | [5 empty] | Not Ordered | [9 empty] | In-Progress | Not Selected |  |  |  | Pending | 0% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  |  | Not Started |  | Pending |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-
GA18C5C-D Emory Decatur Hospital | Not Awarded | Sean Ramjas | (1) Initiated RTP (2) Completed NPA (3) Issued RFP for GC (4) Requested passive material quote and lead time (5) Recieved active material quote and lead time (6) Completed project schedule | Need to design OEM for solution |  | (1) Award project to GCs (2) Finalize budget once quotes are recived (3) Obtain updated CDs per revised Designs. (4) Populate OneVizion once available. (5) Asbestos testing |  | Executed |  |  |  |  | Received | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Customer |  |  |  | Pending | 1% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  | Q4 | Not Started |  | Pending | 442891 | $- | 442891 | 132867.3 |  | 265734.6 |  | 398601.9 |  |  | 326337 | $- | 326337
GA18C61-D Emory Health Sciences Research | Not Awarded | Sean Ramjas | (1) Initiated RTP (2) Completed NPA (3) Issued RFP for GC (4) Requested passive material quote and lead time (5) Recieved active material quote and lead time (6) Completed project schedule |  |  | (1) Award project to GCs (2) Finalize budget once quotes are recived (3) Obtain updated CDs per revised Designs. (4) Populate OneVizion once available. (5) Asbestos testing |  | Executed |  |  |  |  | Received | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Customer |  |  |  | Pending | 1% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  | Q4 | Not Started |  | Pending | 233583 | $- | 233583 | 70074.9 |  | 140149.8 |  | 210224.7 |  |  | 111728 | $- | 111728
GA18C5E-D Emory Hillandale Hospital | Not Awarded | Sean Ramjas | (1) Initiated RTP (2) Completed NPA (3) Issued RFP for GC (4) Requested passive material quote and lead time (5) Recieved active material quote and lead time (6) Completed project schedule | Need to design OEM for solution |  | (1) Award project to GCs (2) Finalize budget once quotes are recived (3) Obtain updated CDs per revised Designs. (4) Populate OneVizion once available. (5) Asbestos testing |  | Executed |  |  |  |  | Started | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Customer |  |  |  | Pending | 1% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  | Q4 | Not Started |  | Pending | 419739 | $- | 419739 | 125921.7 |  | 251843.4 |  | 377765.1 |  |  | 313362 | $- | 313362
GA18C5B-D Emory Hospital Orthopaedics Hospital | Not Awarded | Sean Ramjas | (1) Initiated RTP (2) Completed NPA (3) Issued RFP for GC (4) Requested passive material quote and lead time (5) Recieved active material quote and lead time (6) Completed project schedule | Need to design OEM for solution |  | (1) Award project to GCs (2) Finalize budget once quotes are recived (3) Obtain updated CDs per revised Designs. (4) Populate OneVizion once available. (5) Asbestos testing |  | Executed |  |  |  |  | Started | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Customer |  |  |  | Pending | 1% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  | Q4 | Not Started |  | Pending | 142345 | $- | 142345 | 42703.5 |  | 85407 |  | 128110.5 |  |  | 99496 | $- | 99496
GA18C60-D Emory Long Term Acute Care | Not Awarded | Sean Ramjas | (1) Initiated RTP (2) Completed NPA (3) Issued RFP for GC (4) Requested passive material quote and lead time (5) Recieved active material quote and lead time (6) Completed project schedule |  |  | (1) Award project to GCs (2) Finalize budget once quotes are recived (3) Obtain updated CDs per revised Designs. (4) Populate OneVizion once available. (5) Asbestos testing |  | Executed |  |  |  |  | Started | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Customer |  |  |  | Pending | 1% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  | Q4 | Not Started |  | Pending | 77295 | $- | 77295 | 23188.5 |  | 46377 |  | 69565.5 |  |  | 45297 | $- | 45297
GA18C5D-D Emory University Hospital Midtown | Not Awarded | Sean Ramjas | (1) Initiated RTP (2) Completed NPA (3) Issued RFP for GC (4) Requested passive material quote and lead time (5) Recieved active material quote and lead time (6) Completed project schedule |  |  | (1) Award project to GCs (2) Finalize budget once quotes are recived (3) Obtain updated CDs per revised Designs. (4) Populate OneVizion once available. (5) Asbestos testing |  | Executed |  |  |  |  | Started | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Customer |  |  |  | Pending | 1% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  | Q4 | Not Started |  | Pending | 265184 | $- | 265184 | 79555.2 |  | 159110.4 |  | 238665.6 |  |  | 328819 | $- | 328819
GA18C5F-D Emory Wesley Woods Geriatric Hospital | Not Awarded | Sean Ramjas | (1) Initiated RTP (2) Completed NPA (3) Issued RFP for GC (4) Requested passive material quote and lead time (5) Recieved active material quote and lead time (6) Completed project schedule | Need to design OEM for solution |  | (1) Award project to GCs (2) Finalize budget once quotes are recived (3) Obtain updated CDs per revised Designs. (4) Populate OneVizion once available. (5) Asbestos testing |  | Executed |  |  |  |  | Started | Not Started | In-Process |  |  |  |  | Not Ordered | [9 empty] | In-Progress | Customer |  |  |  | Pending | 1% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  | Q4 | Not Started |  | Pending | 104707 | $- | 104707 | 31412.1 |  | 62824.2 |  | 94236.3 |  |  | 45297 | $- | 45297
UT1B13A-P Valley of Wildflower (Temp Tower #3) | Not Awarded | Sean Ramjas | [5 empty] | Executed |  |  |  |  | Received | Not Started | [5 empty] | Not Ordered | [9 empty] | Not Started | Not Selected |  |  |  | Pending | 0% |  | Pending |  | Not Ordered | Pending |  |  |  | Not Started |  | Not Requested |  | Pending |  |  | Not Started |  | Pending |  |  | $- | $- |  | $- |  | $- |  |  |  |  | $-

## Departmental Milestones
Opportunity to Agreement | Deployment to Operations | Chronological Order of Milestones (From New Tracker) | Additional Milestones | Notes | Field
Sales (BD) | Sales Operations | BD creates opportunity in CRM | ROM Pricing Start Date | Job # | Project ID
|  | BD Name | ROM Pricing Complete Date | Site ID | Job ID
BD creates opportunity in CRM | Start: Executed Agreement | Conduct meeting/call to explore opportunity | A&E Site Walk Date (F) | Site Name | Opportunity ID
Conduct meeting/call to explore opportunity | Prog Manager schedules Kick-off meeting (Est. 3 days) | Explore Opportunity Forecast | A&E Site Walk Date (A) | SBA CM | SBA Site Code
Prospect Interested in proposal |  | Days Passed Since Opportunity Explored | Construction Drawings Received Date (F) | Status | Site Name
BD submits email to NSE | Customer Success Team to assist on training efforts to onboard new users (Vault) | Soft Quote | Construction Drawings Received Date (A) | Notes | Solution
BD reviews fin model pricing |  | Prospect Interested in proposal | Revised Construction Drawings Received Date (F) | Sales Support | Customer Name
BD responds to move fwd | Construction | Date of Prospect Interest | Revised Construction Drawings Received (A) | A&E Vendor | Customer Point of Contact
|  | Days Passed Since Prospect Interest Confirmed | BOM Creation Begins (F) | Construction Drawing Revisions | Customer Escalation
BD submits proposal | Budget Approvals (Est. 7 days) | BD submits email to NSE Design Distro | BOM Creation Begins (A) | Construction Drawing Revisions Number | Carrier Name(s)
Proposal Accepted? | Quotes updates if changes in BOM list (Est. 7 days) | BD Submission to Design Distro Forecast | BOM Creation Complete (F) | OEM Name | Carrier Point(s) of Contact
End/Lost in CRM Update record in CRM | Submit POs (Est. 7 days) | Days Passed Since BD Submission to Design Distro | BOM Creation Complete (Actual) | GC Name | On Hold or Dead
Liaison/review redlines | Coordinate materials logistics (Est. 8 weeks) | Program Manager adds request to tracker | BOM Handoff to Construction (F) | Circuit Needed | On Hold or Dead Reason
| Monitor Construction Start to End (Est. 6 months) | Tracker Update Forecast | BOM Handoff to Construction (A) | Circuit Provider | Stage
Sales Operations | FNE Closeout Package (Est. 2 weeks) | Days Passed Since Tracker Updated | RFPs Received (F) | Construction % Complete | SBA Sales Lead
Program Manager schedules kickoff call to assign action Items & align timelines Est. 2 days |  | Request is MDU? | RFPs Received (A) | Baseline FNE | SBA Proj Contr Mgr
|  |  | GC Bid |  | SBA Proj Coord
Program Manager adds request to tracker | Network Engineering & Design | Opp Name | GC Awarded (F) | Customer POC | SBA Design Lead
Request is MDU? |  | Opp ID | GC Awarded (A) | Landlord POC | SBA Integration Lead
P.M Check with BD OK to submit | Order backhaul (Est. 7 days) | Deal Type | Pre-Construction Site Walk with GC (F) | Carrier(s) POC | Property Type
P.M Submit Request to Aerwave | Final BOM (Est. 7 days) | Property Type | Pre-Construction Site with GC (A) | GC POC | # of Units
Fin Analyst creates fin. model | Core switches configuration (Est. 2 weeks) | #Units | BOM Review with GC (F) | OEM POC | Landlord Point of Contact
Sales Ops Peer review (Est. 7 days) | Backhaul Delivery coordination (Est. 3 months) | SBA or Aerwave | BOM Review with GC (A) | Vendor (POC) | Property Address
Program Manager submits to BD for review (Est. 2 days) | Integration (Est. 2 weeks) | P.M Check with BD OK to submit Aerwave | Materials Ordered (F) | Field | Customer Requirements
Program Manager validates with appropriate teams the pricing data inputs (Est. 2 days) | Site Walk (Est. 2 weeks) | PM Check-in Forecast | Materials Ordered (A) | Project ID | Floor Plans
Program Manager creates 1 pager proposal (Est. 2 days) |  | Days Passed Since PM Check-in | Materials Received (F) | Job ID | Floor Plans
Program Manager creates full proposal (Est. 10 days) | QC/Safety | P.M Submit Request to Aerwave | Materials Received (A) | Opportunity ID | Contract Status
M. Director presents to CAC (Est. 90 days) |  | PM Submission to Aerwave Forecast | Request for RTP Submitted (F) | SBA Site Code | Contract Signed
| QC site review (Est. 7 days) | Days Passed Since PM Submission to Aerwave | Request for RTP Submitted (A) | Site Name | Contract
Network Engineering & Design |  | Program Manager schedules kickoff call to assign action Items & align timelines Est. 2 days | Title Signoff (F) | Solution | Project Kickoff Date
Backhaul pricing Est. 15 days | Network Operations (NOC) | Program Manager Kickoff Forecast | Title Signoff (A) | Customer Name | RTP Submit
Design, ROM (Est. 10 days) |  | Days Passed Since Program Manager Kickoff | Zoning Signoff (F) | Customer Point of Contact | Title
| Accepts Network (Est. 1 week) | Backhaul pricing Est. 15 days | Zoning Signoff (A) | Customer Escalation | Zoning
Construction | End | Backhaul Pricing Forecast | Lease Signoff (F) | Carrier Name(s) | Environmental
OSP Pricing (Est. 10 days) |  | Days Passed Since Backhaul Pricing | Lease Signoff (A) | Carrier Point(s) of Contact | Leasing
|  | Design, ROM (Est. 10 days) ---- | Licensing Signoff (F) | On Hold or Dead | Licensing
|  | Initial Design; Soft ROM |  |  | RTP Approved
Finance/M&A |  | Design, ROM Forecast | Licensing Signoff (A) | On Hold or Dead Reason | Design Walk
Finance Peer review (Est. 7 days) |  | Days Passed Since Design, ROM | Asbestos Testing Required | Stage | A&E Vendor
|  | OSP Pricing (Est. 10 days) | Asbestos Testing Complete (F) | SBA Sales Lead | A&E Point of Contact
Tax |  | OSP Pricing Forecast | Asbestos Testing Complete (A) | SBA Proj Contr Mgr | CDs
Tax fin. model review (Est. 2 days) |  | Days Passed Since OSP Pricing | NPA Signoff (F) | SBA Proj Coord | Original CDs
|  | Fin Analyst creates fin. model | NPA Signoff (A) | SBA Design Lead | Revised CDs
Legal |  | Financial Model Creation Forecast | NEPA Signoff (F) | SBA Integration Lead | Revision #
Draft Agreement (Est. 10 days) |  | Days Passed Since Financial Model Creation | NEPA Signoff (A) | # of Units | Revision Date
Executed Agreement |  | Sales Ops Peer review (Est. 7 days) | RTP Approved (F) | Landlord Point of Contact | Customer Approval of CDs
|  | Sales Ops Peer Review Forecast | RTP Approved (A) | Property Address | Unit Schedule
|  | Days Passed Since Sales Ops Review | Circuit Installed (F) | Customer Requirements | iBwave Design
|  | Finance Peer review (Est. 7 days) | Circuit Installed (A) | Estimated Floor Plans | Original iBwave Design
|  | Finance Peer Review Forecast | Construction Kick-Off Call (F) | Actual Floor Plans | iBwave Design Validation
|  | Days Passed Since Finance Peer Review | Construction Kick-Off Call (A) | Floor Plans | Revised iBwave
|  | Tax fin. model review (Est. 2 days) | Construction Start (F) | Contract Status | Revision # iBwave Design
|  | Tax Financial Model Review Forecast | Construction Start (A) | Contract Signed | Revised iBwave Design
|  | Days Passed Since Tax Fin. Model Review | Construction Complete (F) | Contract | BOM
|  | Program Manager Submits Fin. Model to BD for Review (Est. 2 days) | Construction Complete (A) | % of Fiber In-building | BOM
|  | Program Manager Submits Fin. Model to BD Forecast | Integration Date (F) | % of Fiber Outdoors & Underground | Revision # BOM
|  | Days Passed Since Program Manager submits fin. model to BD | Integration Date (A) | % of Fiber Outdoors & Aboveground | Revised BOM
|  | BD reviews Fin. Model Pricing | COP Received (F) | Estimated CDs | Design and BOM Review
|  | BD Review Forecast | COP Received (A) | Actual CDs | Customer Approval of Design
|  | Days Passed Since BD Reviewed Fin. Model | COP Sent to Network (F) | Revised CDs | Design Notes
|  | BD Responds OK to Move Forward | COP Sent to Network (A) | Revision # | SBA SOW
|  | BD Responds to Move Forward Forecast | COP Accepted by Network (F) | Revision Date | SBA SOW
|  | Days Passed Since BD Responds to Move Forward | COP Accepted by Network (A) | Revised CDs | RFP
|  | Program Manager validates with appropriate teams the pricing data inputs (Est. 2 days) | COP Sent to Customer (F) | Estimated Customer Approval of CDs | Construction GC Selected
|  | ROM; Final Design |  |  | GC
|  | Program Manager Validation Forecast | COP Sent to Customer (A) | Actual Customer Approval of CDs | GC Point of Contact
|  | Days Passed Since Program Manager Validation | COP Acceted by Customer (F) | Estimated Unit Schedule | GC SOW
|  | Program Manager creates 1 pager proposal (Est. 2 days) | COP Accepted by Customer (A) | Actual Unit Schedule | GC Baseline Quote
|  | 1-Pager Proposal Forecast | Handoff to Ops (F) | Design Notes | GC Quote
|  | Days Passed Since Program Manager Creates 1-Pager Proposal | Handoff to Ops (A) | Estimated SBA SOW | IRR
|  | Program Manager creates full proposal (Est. 10 days) | Estimated Backhaul Intallation Date | Actual SBA SOW | IRR
|  | Full Proposal Forecast | Actual Backhaul Installation Date | SBA SOW | Design Handoff to Construction
|  | Days Since Full Proposal | SBA QA Review | GC SOW | Construction Kickoff Call
|  | BD submits proposal | Actual Network Onboarding | GC Baseline Quote | Pre-Construction Walk
|  | BD Submits Proposal Forecast | Estimated Network Testing Start | GC Quote | Order Equipment Date
|  | Days Passed Since BD Submits Proposal | Actual Network Testing Start | Estimated IRR | Equipment Notes
|  | M. Director Presents to CAC (Est. 10 days) | Estimated Network Testing Complete | Actual IRR | Materials Configuration
|  | M. Director Presents to CAC Forecast | Actual Network Testing Complete | IRR | Arrival of Materials to Site
|  | Days Passed Since M. Director Presents to CAC | NOC Network Acceptance Request | Primary Backhaul Provider | Order Backhaul Date
|  | Proposal Accepted? | NOC Network Approval | Primary Backhaul Point of Contact | Backhaul Intallation Date
|  | Proposal Acceptance Date | Request for Customer Approval | Secondary Backhaul Provider | Backhaul Installation Date
|  | Days Since Proposal Accepted | Actual Customer Approval | Secondary Backhaul Provider Point of Contact | Primary Backhaul Provider
|  | Update record in CRM | Estimated FNE Ready | Backhaul Notes | Primary Backhaul Point of Contact
|  | CRM Update Forecast | Actual FNE Ready | TCO Date | Secondary Backhaul Provider
|  | Days Passed Since CRM Update |  | Estimated Revenue Start | Secondary Backhaul Provider Point of Contact
|  | Liaison/review redlines |  | Actual Revenue Start | Backhaul Notes
|  | Liason/Review Redlines Forecast |  | Original Budget $ | Construction
|  | Days Passed Passed Since Liason/Review Redlines |  | Revised Budget $ | % Construction
|  | Draft Agreement (Est. 90 days) |  | JTD Cost | Integration
|  | Draft Agreement Forecast |  | Committed Cost | Network Onboarding
|  | Days Passed Since Agreement Drafted |  | Remaining to Commit | SBA QA Review
|  | Executed Agreement (10 days) |  |  | Network Testing
|  | Agreement Execution Forecast |  |  | Closeout Package Received
|  | Days Passed Since Agreement Executed |  |  | COP Validation
|  | Prog Manager schedules Kick-off meeting (Est. 3 days) |  |  | Legal Notice of Substantial
|  | Kickoff Meeting Forecast |  |  | NOC Network Acceptance Request
|  | Days Passed Since Kickoff Meeting |  |  | NOC Network Approval
|  | Budget Approvals (Est. 7 days) |  |  | Request for Customer Approval
|  | Budget Approval Forecast |  |  | Customer Approval
|  | Days Passed Since Budget Approval |  |  | FNE Baseline
|  | Order backhaul (Est. 7 days) |  |  | FNE Ready
|  | Backhaul Order Forecast |  |  | TCO Date
|  | Days Passed Since Backhaul Ordered |  |  | Revenue
|  | Quotes updates if changes in BOM list (Est. 7 days) |  |  | Revenue
|  | Quote Update Forecast |  |  | Original Budget $
|  | Days Passed Since Quote Updated |  |  | Revised Budget $
|  | Final BOM (Est. 7 days) |  |  | JTD Cost
|  | Final BOM Forecast |  |  | Committed Cost
|  | Days Passed Since Final BOM |  |  | Remaining to Commit
Submit POs (Est. 7 days)
PO Submission Forecast
Days Passed Since PO Submission
RTP
RTP Forecast
Days Since RTP Received
Coordinate materials logistics (Est. 8 weeks)
Materials Logistic Coordination Completion Forecast
Days Passed Since Materials Logistics Coordination Completion
Monitor Construction Start (Est. 6 months)
Construction Start Forecast
Days Passed Since Construction Start
Core switches configuration (Est. 2 weeks)
Core Switch Configuration Forecast
Days Passed Since Core Switch Configuration
Backhaul Delivery coordination (Est. 3 months)
Backhaul Delivery Forecast
Days Passed Since Backhaul Delivery
Integration (Est. 2 weeks)
Integration Completion Forecast
Days Passed Since Integration Completion
Construction Completion
Construction Completion Forecast
Days Passed Since Construction Completion
Optional: Customer Success Team to assist on training efforts to onboard new users (Vault)
QC site review (Est. 7 days)
QC Site Review Forecast
Days Passed Since QC Site Review
Site Walk (Est. 2 weeks)
Site Walk Forecast
Days Passed Since Site Walk
FNE Closeout Package (Est. 2 weeks)
FNE Closeout Package Forecast
Days Passed Since FNE Closeout Package
Accepts Network (Est. 1 week)
Network Acceptance Forecast
Days Passed Since Network Acceptance
Project Completion
Project Completion Forecast
Days Since Project Completion

## OV Milestones
OV | New Tracker | Differences | Differences
Field | BD creates opportunity in CRM | Field | Field
Project ID | BD Name | Project ID | Project ID
Job ID | Conduct meeting/call to explore opportunity | Job ID | Job ID
Opportunity ID | Explore Opportunity Forecast | Opportunity ID | Opportunity ID
SBA Site Code | Days Passed Since Opportunity Explored | SBA Site Code | SBA Site Code
Site Name | Soft Quote | Site Name | Site Name
Solution | Prospect Interested in proposal | Solution | Solution
Customer Name | Date of Prospect Interest | Customer Name | Customer Name
Customer Point of Contact | Days Passed Since Prospect Interest Confirmed | Customer Point of Contact | Customer Point of Contact
Customer Escalation | BD submits email to NSE Design Distro | Customer Escalation | Customer Escalation
Carrier Name(s) | BD Submission to Design Distro Forecast | Carrier Name(s) | Carrier Name(s)
Carrier Point(s) of Contact | Days Passed Since BD Submission to Design Distro | Carrier Point(s) of Contact | Carrier Point(s) of Contact
On Hold or Dead | Program Manager adds request to tracker | On Hold or Dead | On Hold or Dead
On Hold or Dead Reason | Tracker Update Forecast | On Hold or Dead Reason | On Hold or Dead Reason
Stage | Days Passed Since Tracker Updated | Stage | Stage
SBA Sales Lead | Request is MDU? | SBA Sales Lead | SBA Sales Lead
SBA Proj Contr Mgr | Opp Name | SBA Proj Contr Mgr | SBA Proj Contr Mgr
SBA Proj Coord | Opp ID | SBA Proj Coord | SBA Proj Coord
SBA Design Lead | Deal Type | SBA Design Lead | SBA Design Lead
SBA Integration Lead | Property Type | SBA Integration Lead | SBA Integration Lead
Property Type | #Units | # of Units | # of Units
# of Units | SBA or Aerwave | Landlord Point of Contact | Landlord Point of Contact
Landlord Point of Contact | P.M Check with BD OK to submit Aerwave | Property Address | Property Address
Property Address | PM Check-in Forecast | Customer Requirements | Customer Requirements
Customer Requirements | Days Passed Since PM Check-in | Estimated Floor Plans | Estimated Floor Plans
Estimated Floor Plans | P.M Submit Request to Aerwave | Actual Floor Plans | Actual Floor Plans
Actual Floor Plans | PM Submission to Aerwave Forecast | Floor Plans | Floor Plans
Floor Plans | Days Passed Since PM Submission to Aerwave | Contract Status | Contract Status
Contract Status | Program Manager schedules kickoff call to assign action Items & align timelines Est. 2 days | Contract Signed | Contract Signed
Contract Signed | Program Manager Kickoff Forecast | Contract | Contract
Contract | Days Passed Since Program Manager Kickoff | Project Kickoff Date | Project Kickoff Date
Project Kickoff Date | Backhaul pricing Est. 15 days | Estimated RTP Submit | Estimated RTP Submit
Estimated RTP Submit | Backhaul Pricing Forecast | Actual RTP Submit | Actual RTP Submit
Actual RTP Submit | Days Passed Since Backhaul Pricing | Estimated Title | Estimated Title
Estimated Title | Design, ROM (Est. 10 days) | Actual Title | Actual Title
Actual Title | Design, ROM Forecast | Estimated Zoning | Estimated Zoning
Estimated Zoning | Days Passed Since Design, ROM | Actual Zoning | Actual Zoning
Actual Zoning | OSP Pricing (Est. 10 days) | Estimated Environmental | Estimated Environmental
Estimated Environmental | OSP Pricing Forecast | Actual Environmental | Actual Environmental
Actual Environmental | Days Passed Since OSP Pricing | Estimated Leasing | Estimated Leasing
Estimated Leasing | Fin Analyst creates fin. model | Actual Leasing | Actual Leasing
Actual Leasing | Financial Model Creation Forecast | Estimated Licensing | Estimated Licensing
Estimated Licensing | Days Passed Since Financial Model Creation | Actual Licensing | Actual Licensing
Actual Licensing | Sales Ops Peer review (Est. 7 days) | Estimated RTP Approved | Estimated RTP Approved
Estimated RTP Approved | Sales Ops Peer Review Forecast | Actual RTP Approved | Actual RTP Approved
Actual RTP Approved | Days Passed Since Sales Ops Review | Estimated Design Walk | Estimated Design Walk
Estimated Design Walk | Finance Peer review (Est. 7 days) | Actual Design Walk | Actual Design Walk
Actual Design Walk | Finance Peer Review Forecast | A&E Vendor | A&E Vendor
A&E Vendor | Days Passed Since Finance Peer Review | A&E Point of Contact | A&E Point of Contact
A&E Point of Contact | Tax fin. model review (Est. 2 days) | Estimated CDs | Estimated CDs
Estimated CDs | Tax Financial Model Review Forecast | Actual CDs | Actual CDs
Actual CDs | Days Passed Since Tax Fin. Model Review | Original CDs | Original CDs
Original CDs | Program Manager Submits Fin. Model to BD for Review (Est. 2 days) | Revised CDs | Revised CDs
Revised CDs | Program Manager Submits Fin. Model to BD Forecast | Revision # | Revision #
Revision # | Days Passed Since Program Manager submits fin. model to BD | Revision Date | Revision Date
Revision Date | BD reviews Fin. Model Pricing | Revised CDs | Revised CDs
Revised CDs | BD Review Forecast | Estimated Customer Approval of CDs | Estimated Customer Approval of CDs
Estimated Customer Approval of CDs | Days Passed Since BD Reviewed Fin. Model | Actual Customer Approval of CDs | Actual Customer Approval of CDs
Actual Customer Approval of CDs | BD Responds OK to Move Forward | Estimated Unit Schedule | Estimated Unit Schedule
Estimated Unit Schedule | BD Responds to Move Forward Forecast | Actual Unit Schedule | Actual Unit Schedule
Actual Unit Schedule | Days Passed Since BD Responds to Move Forward | Estimated iBwave Design | Estimated iBwave Design
Estimated iBwave Design | Program Manager validates with appropriate teams the pricing data inputs (Est. 2 days) | Actual iBwave Design | Actual iBwave Design
Actual iBwave Design | Program Manager Validation Forecast | Original iBwave Design | Original iBwave Design
Original iBwave Design | Days Passed Since Program Manager Validation | iBwave Design Validation Complete | iBwave Design Validation Complete
iBwave Design Validation Complete | Program Manager creates 1 pager proposal (Est. 2 days) | Revised iBwave | Revised iBwave
Revised iBwave | 1-Pager Proposal Forecast | Revision # iBwave Design | Revision # iBwave Design
Revision # iBwave Design | Days Passed Since Program Manager Creates 1-Pager Proposal | Revised iBwave Design | Revised iBwave Design
Revised iBwave Design | Program Manager creates full proposal (Est. 10 days) | Estimated BOM | Estimated BOM
Estimated BOM | Full Proposal Forecast | Actual BOM | Actual BOM
Actual BOM | Days Since Full Proposal | BOM | BOM
BOM | BD submits proposal | Revision # BOM | Revision # BOM
Revision # BOM | BD Submits Proposal Forecast | Revised BOM | Revised BOM
Revised BOM | Days Passed Since BD Submits Proposal | Revised BOM | Revised BOM
Revised BOM | M. Director Presents to CAC (Est. 10 days) | Estimated Design and BOM Review | Estimated Design and BOM Review
Estimated Design and BOM Review | M. Director Presents to CAC Forecast | Actual Design and BOM Review | Actual Design and BOM Review
Actual Design and BOM Review | Days Passed Since M. Director Presents to CAC | Estimated Customer Approval of Design | Estimated Customer Approval of Design
Estimated Customer Approval of Design | Proposal Accepted? | Actual Customer Approval of Design | Actual Customer Approval of Design
Actual Customer Approval of Design | Proposal Acceptance Date | Design Notes | Design Notes
Design Notes | Days Since Proposal Accepted | Estimated SBA SOW | Estimated SBA SOW
Estimated SBA SOW | Update record in CRM | Actual SBA SOW | Actual SBA SOW
Actual SBA SOW | CRM Update Forecast | SBA SOW | SBA SOW
SBA SOW | Days Passed Since CRM Update | Estimated RFP Start | Estimated RFP Start
Estimated RFP Start | Liaison/review redlines | Actual RFP Complete | Actual RFP Complete
Actual RFP Complete | Liason/Review Redlines Forecast | Estimated RFP Complete | Estimated RFP Complete
Estimated RFP Complete | Days Passed Passed Since Liason/Review Redlines | Actual RFP Complete | Actual RFP Complete
Actual RFP Complete | Draft Agreement (Est. 90 days) | Estimated Construction GC Selected | Estimated Construction GC Selected
Estimated Construction GC Selected | Draft Agreement Forecast | Actual Construction GC Selected | Actual Construction GC Selected
Actual Construction GC Selected | Days Passed Since Agreement Drafted | GC | GC
GC | Executed Agreement (10 days) | GC Point of Contact | GC Point of Contact
GC Point of Contact | Agreement Execution Forecast | GC SOW | GC SOW
GC SOW | Days Passed Since Agreement Executed | GC Baseline Quote | GC Baseline Quote
GC Baseline Quote | Prog Manager schedules Kick-off meeting (Est. 3 days) | GC Quote | GC Quote
GC Quote | Kickoff Meeting Forecast | Estimated IRR | Estimated IRR
Estimated IRR | Days Passed Since Kickoff Meeting | Actual IRR | Actual IRR
Actual IRR | Budget Approvals (Est. 7 days) | IRR | IRR
IRR | Budget Approval Forecast | Estimated Design Handoff to Construction | Estimated Design Handoff to Construction
Estimated Design Handoff to Construction | Days Passed Since Budget Approval | Actual Design Handoff to Construction | Actual Design Handoff to Construction
Actual Design Handoff to Construction | Order backhaul (Est. 7 days) | Estimated Construction Kickoff Call | Estimated Construction Kickoff Call
Estimated Construction Kickoff Call | Backhaul Order Forecast | Actual Construction Kickoff Call | Actual Construction Kickoff Call
Actual Construction Kickoff Call | Days Passed Since Backhaul Ordered | Estimated Pre-Construction Walk | Estimated Pre-Construction Walk
Estimated Pre-Construction Walk | Quotes updates if changes in BOM list (Est. 7 days) | Actual Pre-Construction Walk | Actual Pre-Construction Walk
Actual Pre-Construction Walk | Quote Update Forecast | Estimated Order Equipment Date | Estimated Order Equipment Date
Estimated Order Equipment Date | Days Passed Since Quote Updated | Actual Order Equipment Date | Actual Order Equipment Date
Actual Order Equipment Date | Final BOM (Est. 7 days) | Equipment Notes | Equipment Notes
Equipment Notes | Final BOM Forecast | Estimated Materials Configuration Start | Estimated Materials Configuration Start
Estimated Materials Configuration Start | Days Passed Since Final BOM | Actual Materials Configuration Start | Actual Materials Configuration Start
Actual Materials Configuration Start | Submit POs (Est. 7 days) | Estimated Materials Configuration Complete | Estimated Materials Configuration Complete
Estimated Materials Configuration Complete | PO Submission Forecast | Actual Materials Configuration Complete | Actual Materials Configuration Complete
Actual Materials Configuration Complete | Days Passed Since PO Submission | Estimated Arrival of Materials to Site | Estimated Arrival of Materials to Site
Estimated Arrival of Materials to Site | RTP | Actual Arrival of Materials to Site | Actual Arrival of Materials to Site
Actual Arrival of Materials to Site | RTP Forecast | Estimated Order Backhaul Date | Estimated Order Backhaul Date
Estimated Order Backhaul Date | Days Since RTP Received | Actual Order Backhaul Date | Actual Order Backhaul Date
Actual Order Backhaul Date | Coordinate materials logistics (Est. 8 weeks) | Estimated Backhaul Intallation Date | Estimated Backhaul Intallation Date
Estimated Backhaul Intallation Date | Materials Logistic Coordination Completion Forecast | Actual Backhaul Installation Date | Actual Backhaul Installation Date
Actual Backhaul Installation Date | Days Passed Since Materials Logistics Coordination Completion | Primary Backhaul Provider | Primary Backhaul Provider
Primary Backhaul Provider | Monitor Construction Start (Est. 6 months) | Primary Backhaul Point of Contact | Primary Backhaul Point of Contact
Primary Backhaul Point of Contact | Construction Start Forecast | Secondary Backhaul Provider | Secondary Backhaul Provider
Secondary Backhaul Provider | Days Passed Since Construction Start | Secondary Backhaul Provider Point of Contact | Secondary Backhaul Provider Point of Contact
Secondary Backhaul Provider Point of Contact | Core switches configuration (Est. 2 weeks) | Backhaul Notes | Backhaul Notes
Backhaul Notes | Core Switch Configuration Forecast | Estimated Construction Start | Estimated Construction Start
Estimated Construction Start | Days Passed Since Core Switch Configuration | Actual Construction Start | Actual Construction Start
Actual Construction Start | Backhaul Delivery coordination (Est. 3 months) | % Construction Complete | % Construction Complete
% Construction Complete | Backhaul Delivery Forecast | Estimated Construction Complete | Estimated Construction Complete
Estimated Construction Complete | Days Passed Since Backhaul Delivery | Actual Construction Complete | Actual Construction Complete
Actual Construction Complete | Integration (Est. 2 weeks) | Estimated Integration Start | Estimated Integration Start
Estimated Integration Start | Integration Completion Forecast | Actual Integration Start | Actual Integration Start
Actual Integration Start | Days Passed Since Integration Completion | Estimated Integration Complete | Estimated Integration Complete
Estimated Integration Complete | Construction Completion | Actual Integration Complete | Actual Integration Complete
Actual Integration Complete | Construction Completion Forecast | Estimated Network Onboarding | Estimated Network Onboarding
Estimated Network Onboarding | Days Passed Since Construction Completion | SBA QA Review | SBA QA Review
SBA QA Review | Optional: Customer Success Team to assist on training efforts to onboard new users (Vault) | Actual Network Onboarding | Actual Network Onboarding
Actual Network Onboarding | QC site review (Est. 7 days) | Estimated Network Testing Start | Estimated Network Testing Start
Estimated Network Testing Start | QC Site Review Forecast | Actual Network Testing Start | Actual Network Testing Start
Actual Network Testing Start | Days Passed Since QC Site Review | Estimated Network Testing Complete | Estimated Network Testing Complete
Estimated Network Testing Complete | Site Walk (Est. 2 weeks) | Actual Network Testing Complete | Actual Network Testing Complete
Actual Network Testing Complete | Site Walk Forecast | Estimated Closeout Package Received | Estimated Closeout Package Received
Estimated Closeout Package Received | Days Passed Since Site Walk | Actual Closeout Package Received | Actual Closeout Package Received
Actual Closeout Package Received | FNE Closeout Package (Est. 2 weeks) | Estimated COP Validation | Estimated COP Validation
Estimated COP Validation | FNE Closeout Package Forecast | Actual COP Validation | Actual COP Validation
Actual COP Validation | Days Passed Since FNE Closeout Package | Legal Notice of Substantial Complete | Legal Notice of Substantial Complete
Legal Notice of Substantial Complete | Accepts Network (Est. 1 week) | NOC Network Acceptance Request | NOC Network Acceptance Request
NOC Network Acceptance Request | Network Acceptance Forecast | NOC Network Approval | NOC Network Approval
NOC Network Approval | Days Passed Since Network Acceptance | Request for Customer Approval | Request for Customer Approval
Request for Customer Approval | Project Completion | Actual Customer Approval | Actual Customer Approval
Actual Customer Approval | Project Completion Forecast | FNE Baseline | FNE Baseline
FNE Baseline | Days Since Project Completion | Estimated FNE Ready | Estimated FNE Ready
Estimated FNE Ready |  | Actual FNE Ready | Actual FNE Ready
Actual FNE Ready |  | TCO Date | TCO Date
TCO Date |  | Estimated Revenue Start | Estimated Revenue Start
Estimated Revenue Start |  | Actual Revenue Start | Actual Revenue Start
Actual Revenue Start |  | Original Budget $ | Original Budget $
Original Budget $ |  | Revised Budget $ | Revised Budget $
Revised Budget $ |  | JTD Cost | JTD Cost
JTD Cost |  | Committed Cost | Committed Cost
Committed Cost |  | Remaining to Commit | Remaining to Commit
Remaining to Commit

## Construction Milestone (AC)
DAS Tracker Milestones | New Tracker Milestones | Differences | Differences
Job # | BD creates opportunity in CRM | Job # | Job #
Site ID | BD Name | Site ID | Site ID
Site Name | Conduct meeting/call to explore opportunity | Site Name | Site Name
SBA CM | Explore Opportunity Forecast | SBA CM | SBA CM
Status | Days Passed Since Opportunity Explored | Status | Status
Notes | Soft Quote | Notes | Notes
Sales Support | Prospect Interested in proposal | Sales Support | Sales Support
ROM Pricing Start Date | Date of Prospect Interest | ROM Pricing Start Date | ROM Pricing Start Date
ROM Pricing Complete Date | Days Passed Since Prospect Interest Confirmed | ROM Pricing Complete Date | ROM Pricing Complete Date
A&E Vendor | BD submits email to NSE Design Distro | A&E Vendor | A&E Vendor
A&E Site Walk Date (F) | BD Submission to Design Distro Forecast | A&E Site Walk Date (F) | A&E Site Walk Date (F)
A&E Site Walk Date (A) | Days Passed Since BD Submission to Design Distro | A&E Site Walk Date (A) | A&E Site Walk Date (A)
Construction Drawings Received Date (F) | Program Manager adds request to tracker | Construction Drawings Received Date (F) | Construction Drawings Received Date (F)
Construction Drawings Received Date (A) | Tracker Update Forecast | Construction Drawings Received Date (A) | Construction Drawings Received Date (A)
Construction Drawing Revisions | Days Passed Since Tracker Updated | Construction Drawing Revisions | Construction Drawing Revisions
Construction Drawing Revisions Number | Request is MDU? | Construction Drawing Revisions Number | Construction Drawing Revisions Number
Revised Construction Drawings Received Date (F) | Opp Name | Revised Construction Drawings Received Date (F) | Revised Construction Drawings Received Date (F)
Revised Construction Drawings Received (A) | Opp ID | Revised Construction Drawings Received (A) | Revised Construction Drawings Received (A)
BOM Creation Begins (F) | Deal Type | BOM Creation Begins (F) | BOM Creation Begins (F)
BOM Creation Begins (A) | Property Type | BOM Creation Begins (A) | BOM Creation Begins (A)
BOM Creation Complete (F) | #Units | BOM Creation Complete (F) | BOM Creation Complete (F)
BOM Creation Complete (Actual) | SBA or Aerwave | BOM Creation Complete (Actual) | BOM Creation Complete (Actual)
BOM Handoff to Construction (F) | P.M Check with BD OK to submit Aerwave | BOM Handoff to Construction (F) | BOM Handoff to Construction (F)
BOM Handoff to Construction (A) | PM Check-in Forecast | BOM Handoff to Construction (A) | BOM Handoff to Construction (A)
RFPs Received (F) | Days Passed Since PM Check-in | RFPs Received (F) | RFPs Received (F)
RFPs Received (A) | P.M Submit Request to Aerwave | RFPs Received (A) | RFPs Received (A)
GC Awarded (F) | PM Submission to Aerwave Forecast | GC Awarded (F) | GC Awarded (F)
GC Awarded (A) | Days Passed Since PM Submission to Aerwave | GC Awarded (A) | GC Awarded (A)
OEM Name | Program Manager schedules kickoff call to assign action Items & align timelines Est. 2 days | OEM Name | OEM Name
GC Name | Program Manager Kickoff Forecast | GC Name | GC Name
Pre-Construction Site Walk with GC (F) | Days Passed Since Program Manager Kickoff | Pre-Construction Site Walk with GC (F) | Pre-Construction Site Walk with GC (F)
Pre-Construction Site with GC (A) | Backhaul pricing Est. 15 days | Pre-Construction Site with GC (A) | Pre-Construction Site with GC (A)
BOM Review with GC (F) | Backhaul Pricing Forecast | BOM Review with GC (F) | BOM Review with GC (F)
BOM Review with GC (A) | Days Passed Since Backhaul Pricing | BOM Review with GC (A) | BOM Review with GC (A)
Materials Ordered (F) | Design, ROM (Est. 10 days) | Materials Ordered (F) | Materials Ordered (F)
Materials Ordered (A) | Initial Design, ROM Draft | Materials Ordered (A) | Materials Ordered (A)
Materials Received (F) | Days Passed Since Design, ROM | Materials Received (F) | Materials Received (F)
Materials Received (A) | OSP Pricing (Est. 10 days) | Materials Received (A) | Materials Received (A)
Request for RTP Submitted (F) | OSP Pricing Forecast | Request for RTP Submitted (F) | Request for RTP Submitted (F)
Request for RTP Submitted (A) | Days Passed Since OSP Pricing | Request for RTP Submitted (A) | Request for RTP Submitted (A)
Title Signoff (F) | Fin Analyst creates fin. model | Title Signoff (F) | Title Signoff (F)
Title Signoff (A) | Financial Model Creation Forecast | Title Signoff (A) | Title Signoff (A)
Zoning Signoff (F) | Days Passed Since Financial Model Creation | Zoning Signoff (F) | Zoning Signoff (F)
Zoning Signoff (A) | Sales Ops Peer review (Est. 7 days) | Zoning Signoff (A) | Zoning Signoff (A)
Lease Signoff (F) | Sales Ops Peer Review Forecast | Lease Signoff (F) | Lease Signoff (F)
Lease Signoff (A) | Days Passed Since Sales Ops Review | Lease Signoff (A) | Lease Signoff (A)
Licensing Signoff (F) | Finance Peer review (Est. 7 days) | Licensing Signoff (F) | Licensing Signoff (F)
Licensing Signoff (A) | Finance Peer Review Forecast | Licensing Signoff (A) | Licensing Signoff (A)
Asbestos Testing Required | Days Passed Since Finance Peer Review | Asbestos Testing Required | Asbestos Testing Required
Asbestos Testing Complete (F) | Tax fin. model review (Est. 2 days) | Asbestos Testing Complete (F) | Asbestos Testing Complete (F)
Asbestos Testing Complete (A) | Tax Financial Model Review Forecast | Asbestos Testing Complete (A) | Asbestos Testing Complete (A)
NPA Signoff (F) | Days Passed Since Tax Fin. Model Review | NPA Signoff (F) | NPA Signoff (F)
NPA Signoff (A) | Program Manager Submits Fin. Model to BD for Review (Est. 2 days) | NPA Signoff (A) | NPA Signoff (A)
NEPA Signoff (F) | Program Manager Submits Fin. Model to BD Forecast | NEPA Signoff (F) | NEPA Signoff (F)
NEPA Signoff (A) | Days Passed Since Program Manager submits fin. model to BD | NEPA Signoff (A) | NEPA Signoff (A)
RTP Approved (F) | BD reviews Fin. Model Pricing | RTP Approved (F) | RTP Approved (F)
RTP Approved (A) | BD Review Forecast | RTP Approved (A) | RTP Approved (A)
Circuit Needed | Days Passed Since BD Reviewed Fin. Model | Circuit Needed | Circuit Needed
Circuit Provider | BD Responds OK to Move Forward | Circuit Provider | Circuit Provider
Circuit Installed (F) | BD Responds to Move Forward Forecast | Circuit Installed (F) | Circuit Installed (F)
Circuit Installed (A) | Days Passed Since BD Responds to Move Forward | Circuit Installed (A) | Circuit Installed (A)
Construction Kick-Off Call (F) | Program Manager validates with appropriate teams the pricing data inputs (Est. 2 days) | Construction Kick-Off Call (F) | Construction Kick-Off Call (F)
Construction Kick-Off Call (A) | Program Manager Validation Forecast | Construction Kick-Off Call (A) | Construction Kick-Off Call (A)
Construction Start (F) | Days Passed Since Program Manager Validation | Construction Start (F) | Construction Start (F)
Construction Start (A) | Program Manager creates 1 pager proposal (Est. 2 days) | Construction Start (A) | Construction Start (A)
Construction % Complete | 1-Pager Proposal Forecast | Construction % Complete | Construction % Complete
Construction Complete (F) | Days Passed Since Program Manager Creates 1-Pager Proposal | Construction Complete (F) | Construction Complete (F)
Construction Complete (A) | Program Manager creates full proposal (Est. 10 days) | Construction Complete (A) | Construction Complete (A)
Integration Date (F) | Full Proposal Forecast | Integration Date (F) | Integration Date (F)
Integration Date (A) | Days Since Full Proposal | Integration Date (A) | Integration Date (A)
COP Received (F) | BD submits proposal | COP Received (F) | COP Received (F)
COP Received (A) | BD Submits Proposal Forecast | COP Received (A) | COP Received (A)
COP Sent to Network (F) | Days Passed Since BD Submits Proposal | COP Sent to Network (F) | COP Sent to Network (F)
COP Sent to Network (A) | M. Director Presents to CAC (Est. 10 days) | COP Sent to Network (A) | COP Sent to Network (A)
COP Accepted by Network (F) | M. Director Presents to CAC Forecast | COP Accepted by Network (F) | COP Accepted by Network (F)
COP Accepted by Network (A) | Days Passed Since M. Director Presents to CAC | COP Accepted by Network (A) | COP Accepted by Network (A)
COP Sent to Customer (F) | Proposal Accepted? | COP Sent to Customer (F) | COP Sent to Customer (F)
COP Sent to Customer (A) | Proposal Acceptance Date | COP Sent to Customer (A) | COP Sent to Customer (A)
COP Acceted by Customer (F) | Days Since Proposal Accepted | COP Acceted by Customer (F) | COP Acceted by Customer (F)
COP Accepted by Customer (A) | Update record in CRM | COP Accepted by Customer (A) | COP Accepted by Customer (A)
Baseline FNE | CRM Update Forecast | Baseline FNE | Baseline FNE
FNE (F) | Days Passed Since CRM Update | FNE (F) | FNE (F)
FNE (A) | Liaison/review redlines | FNE (A) | FNE (A)
Handoff to Ops (F) | Liason/Review Redlines Forecast | Handoff to Ops (F) | Handoff to Ops (F)
Handoff to Ops (A) | Days Passed Passed Since Liason/Review Redlines | Handoff to Ops (A) | Handoff to Ops (A)
Customer POC | Draft Agreement (Est. 90 days) | Customer POC | Customer POC
Landlord POC | Draft Agreement Forecast | Landlord POC | Landlord POC
Carrier(s) POC | Days Passed Since Agreement Drafted | Carrier(s) POC | Carrier(s) POC
GC POC | Executed Agreement (10 days) | GC POC | GC POC
OEM POC | Agreement Execution Forecast | OEM POC | OEM POC
Vendor (POC) | Days Passed Since Agreement Executed | Vendor (POC) | Vendor (POC)
Prog Manager schedules Kick-off meeting (Est. 3 days)
Kickoff Meeting Forecast
Days Passed Since Kickoff Meeting
Budget Approvals (Est. 7 days)
Budget Approval Forecast
Days Passed Since Budget Approval
Order backhaul (Est. 7 days)
Backhaul Order Forecast
Days Passed Since Backhaul Ordered
Quotes updates if changes in BOM list (Est. 7 days)
Quote Update Forecast
Days Passed Since Quote Updated
Final BOM (Est. 7 days)
Final BOM Forecast
Days Passed Since Final BOM
Submit POs (Est. 7 days)
PO Submission Forecast
Days Passed Since PO Submission
RTP
RTP Forecast
Days Since RTP Received
Coordinate materials logistics (Est. 8 weeks)
Materials Logistic Coordination Completion Forecast
Days Passed Since Materials Logistics Coordination Completion
Monitor Construction Start (Est. 6 months)
Construction Start Forecast
Days Passed Since Construction Start
Core switches configuration (Est. 2 weeks)
Core Switch Configuration Forecast
Days Passed Since Core Switch Configuration
Backhaul Delivery coordination (Est. 3 months)
Backhaul Delivery Forecast
Days Passed Since Backhaul Delivery
Integration (Est. 2 weeks)
Integration Completion Forecast
Days Passed Since Integration Completion
Construction Completion
Construction Completion Forecast
Days Passed Since Construction Completion
Optional: Customer Success Team to assist on training efforts to onboard new users (Vault)
QC site review (Est. 7 days)
QC Site Review Forecast
Days Passed Since QC Site Review
Site Walk (Est. 2 weeks)
Site Walk Forecast
Days Passed Since Site Walk
FNE Closeout Package (Est. 2 weeks)
FNE Closeout Package Forecast
Days Passed Since FNE Closeout Package
Accepts Network (Est. 1 week)
Network Acceptance Forecast
Days Passed Since Network Acceptance
Project Completion
Project Completion Forecast
Days Since Project Completion